## FINAL SDBIP 1920
AMENED TOP LVEL SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP): ORGANISATIONAL SCORECARD
NAME OF MUNICIPALITY: UTHUKELA DISTRICT MUNICIPALITY
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | INDICATORS | Unit of Measure | Ward No. | ANNUAL TARGET | 2018/2019 |  |  | Q1 | Q1 Actual | Q2 | Q2 Actual | Achieved/Not Achieved | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog | Projected Target |  | Projected Target
KPA 1: MUNICIPAL TRANFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID01 | To ensure functional Performance Management System implemented | Implementation of PMS Policy & Framework | Date of review and adoption of PMS Policy and Proceduaral Framework by Council by 30/06/2020 | Date | n/a | Adoption of PMS Policy and Proceduaral Framework by 30/05/2020 | Adoption of PMS Policy and Proceduaral Framework by 30/05/2020 | PMS Policy and Proceduaral Framework reviewed and adopted on 18/05/2019 | n/a | n/a | n/a | n/a | n/a | n/a | Office of the MM | OPEX | Council resolution and copy of the PMS Policy and Proceduaral Framework
MTID02 |  |  | Number of quarterly performance management reports submitted to Council by 30/06/2020 | Number | n/a | Four (4) quarterly performance management reports submitted to Council by 30/06/2020 | Four (4) quarterly performance management reports submitted to Council by 30/06/2020 | Four (4) quarterly performance management reports submitted to Council by 30/06/2019 | n/a | One (1) quarterly performance management report submitted to Council by 31/10/2019 | One (1) quarterly performance management report was submitted to Council on the 31/10/2019 | One (1) quarterly performance management report submitted to Council by 31/01/2019 | One (1) quarterly performance management report submitted to Council by 31/01/2019 | Achieved | Office of the MM | OPEX | Council resolutions and Quarterly reports
MTID03 |  |  | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2020 | Date | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2020 | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2020 | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2019 | n/a | n/a | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2019 | Mid-Year Performance Report submitted to the Mayor and Treasuries by 25/01/2019 | Achieved | Office of the MM | OPEX | Proof of submission and Mid-Year Performance Report
MTID04 |  |  | Date of submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Date | n/a | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2018 | n/a | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Unaudited Annual Performance Report was submitted to the Auditor-General on the 31/08/2019 | n/a | n/a | n/a | Office of the MM | OPEX | Proof of submission and Annual Performance Report
MTID1.5 |  |  | Date table of Annual Report to Council by 31/01/2020 | Date | n/a | Tabling of Annual Report to Council by 31/01/2020 | Tabling of Annual Report to Council by 31/01/2020 | Annual Report tabled to Council by 26/01/2019 | n/a | n/a | n/a | Tabling of Annual Report to Council by 31/01/2020 | The Annual Report was tabled to Council on the 24/01/2020 | Achieved | Office of the MM | OPEX | Council resolution
MTID06 |  |  | Number of section 54/56 managers ‘performance reviews conducted per financial year |  |  | 2 Performance reviews conducted by 30/06/2020 | 2 Performance reviews conducted by 30/06/2020 |  | n/a | n/a | n/a | n/a | n/a | n/a | Office of the MM | OPEX | Signed Assessment Reports
MTID07 | To ensure fucntional risk management | Review and adopt risk management fraework | Date of review and adoption of risk management framework by Council by 30/06/2020 | Date | n/a | Review and adoption of risk management framework by Council by 30/06/2020 | Review and adoption of risk management framework by Council by 30/06/2020 | Risk management framework reviewed and adopted by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | n/a | Office of the MM | OPEX | Council resolution and risk management framework
MTID08 | To Improve organisational Capacity | Review of organisational structure | Number of organizational structures reviewed and adopted by Council by 30/06/2020 | Number | n/a | One (1) organizational structures reviewed and adopted by Council by 30/06/2020 | One (1) organizational structures reviewed and adopted by Council by 30/06/2020 | One (1) organizational structures reviewed and adopted by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | n/a | Corporate Services | OPEX | Council Resoution and copy of the organisational structure
MTID09 |  | Employment equity plan adopted | Number of people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2020 | Number | n/a | Two (2) people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2020 | Two (2) people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan 30/06/2020 | n/a | n/a | n/a | n/a | n/a |  |  | Corporate Services | OPEX | Employment Equity Plan and appointment letters
MTID10 |  | Implementation of Workplace Skills Plan | Percentage of budget spent in the implementation of Workplace Skills Plan by 30/06/2020 | Percentage | n/a | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2020 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2020 | Sixty (60%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2019 | Forty (40%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2020 | Twenty Five (25%) of budget spent in the implementation of Workplace Skills Plan by 31/08/2019 | (0) No budget was spent in the implementation of Workplace Skills Plan by 31/08/2019 | Fifty (50%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2019 | 11,2% of budget was spent in the implementation of Workplace Skills Plan by 31/12/2019 | Not Achieved | Corporate Services | OPEX | Signed training reports
MTID11 | To ensure an effective and efficient HR systems that addresses Human resources within the municipality | Review and adotion of HR related policies | Date to review and adopt HR related policies by Council by 30/06/2020 | Date | n/a | Review and adoption of HR related policies by Council by 30/06/2020 | Review and adoption of HR related policies by Council by 30/06/2019 | HR related policies reviewed and adopted by Council by 30/04/2018 | n/a | n/a | n/a | n/a | n/a | n/a | Corporate Services | OPEX | HR related policies & Council Resolution
MTID12 | To ensure effective and efficient internal and external communication strategy. | Review and adoption of Communication Strategy | Date of review and adotion of communication strategy by Council by 30/06/2020 | Date | n/a | Review and adotion of communication strategy by Councl by 30/06/2020 | Review and adotion of communication strategy by Councl by 30/06/2019 | Communication strategy reviewed and adopted by Councl by 30/06/2018 | n/a | n/a | n/a | n/a | n/a | n/a | Office of the MM | OPEX | Communication Strategy & Council Resolution
MTID13 | To report & monitor Service Delivery | Submission of quarterly reports to Cogta | Number of B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2020 | Number | n/a | Four (4) 4B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2020 | Four (4) 4B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2020 | Four (4) 4B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2019 | n/a | One (1) B2B Quarterly Performance Report and support plan submitted to Provincial Cogta by 27/10/2019 | One (1) B2B Quarterly Performance Report and support plan was submitted to Provincial Cogta by 27/10/2019 | One (1) B2B Quarterly Performance Report and support plan submitted to Provincial Cogta by 27/01/2020 | One (1) B2B Quarterly Performance Report and support plan was submitted to Provincial Cogta by 27/01/2020 | Achieved | Office of the MM | OPEX | B2B Report, Proof of submission
MTID14 | To improve the municipal Audit opinion | Effective Audit and Performance Committee | Number of Audit and Performance Committee meetings held by 30/06/2020 | Number | n/a | Four (4) Audit and Performance Committee meetings held by 30/06/2020 | Four (4) Audit and Performance Committee meetings held by 30/06/2020 | Six (6) Audit and Performance Committee meetings held by 30/06/2019 | n/a | Four (1) Audit and Performance Committee meetings held by 30/09/2019 | Two (2) Audit and Performance Committee meetings were held on the 24/08/2019 and 08/08/2019 | One (1) Audit and Performance Committee meetings held by 30/06/2019 | One (1) Audit and Performance Committee meetings held on the 25/10/2019 | Achieved | Office of the MM | OPEX | Notice, minutes & attendance registers
MTID15 |  | Oversight meetings held | Number of MPAC meetings convened by 30/06/2020 | Number | n/a | Four (4) MPAC meetings convened by 30/06/2020 | Four (4) MPAC meetings convened by 30/06/2020 | Eight (8) MPAC meetings convened by 30/06/2019 | n/a | One (1) MPAC meeting convened by 30/09/2019 | One (1) MPAC meeting convened on the 28/08/2019 | One (1) MPAC meeting convened on the 31/12/2019 | One (1) MPAC meeting convened on the 27/11/2019 | Achieved | Office of the MM | OPEX | Notice, minutes & attendance registers
KPA2: BASIC SERVICE DELIVERY
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | INDICATORS | Unit of Measure | Ward No. | ANNUAL TARGET | 2018/19 |  |  | Q1 | Q1 Actual | Q2 | Q2 Actual | Achieved/Not Achieved | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog | Projected Target |  | Projected Target
BSD 01 | To provide infrastructure and sustainable basic services | Provide community water supply | Number of Reservoirs constructed on MIG related projects by 30/06/2020 ( Ntabamhlophe phase 13,376KL reservoir at Fitty Park Supply Scheme,100kilo liters of Resevour constructed at Oliphantsskop Water Traetments Works) | Number |  | Three (3)Reservoirs constructed on MIG related projects by 30/06/2020 (One(1)Reservors completed at Ntabamhlophe phase 13, One(1)376KL reservoir at Fitty Park Supply Scheme) (1) of 100kilo liters of Resevour constructed at Oliphantsskop Water Traetments Works | One(1)Reservors completed at Ntabamhlophe phase 13 by 30/12/2020 | One(1)Reservors completed at Ntabamhlophe phase 13 by 30/12/2020 | One(1)Reservors completed at Ntabamhlophe phase 13 by 30/12/2020 | n/a | n/a | One Reservoirs constructed at Ntabamhlophe Phase 13 by 31/12/2019 | One Reservoirs constructed at Ntabamhlophe Phase 13 by 31/12/2019 | Achieved | Water,Sanitation and Technical Services | MIG ALLOCATION | Signed Engineers Report
[7 empty] | Completion of 376KL reservoir at Fitty Park Supply Scheme by 30/06/2020 | New Indiactor | New Indicator
[7 empty] | One(1) of 100kilo liters of Resevour constructed at Oliphantsskop Water Traetments Works by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD02 |  |  | Kilometers of Reticulation Lines constructed on the MIG related Projects by 30/06/2020 (Ntabamhlophe Emergency Repairs,Kwanobamba Ezitendeni,Bergville Phase 2) | Kilometers |  | 500 Meters of Reticulation line constructed Ntabamhlophe Emergency Repairs Project by 30/06/2020 | km of Reticulation line constructed Ntabamhlophe Emergency Repairs Project by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
[6 empty] | km of Reticulation Lines Constructed at Kwanobamba Ezitendeni Water Supply by 30 June 2020 | km of Reticulation Lines Constructed at Kwanobamba Ezitendeni Water Supply by 30 June 2020 | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD03 |  |  | Kilometres of bulk lines constructed on the MIG related projects by 30/06/2020 (Bergville Phase 1,Raw Water Bulk Line constructed at Kwanobamba Ezitendeni,Ekuvukeni Water) | Kilometres |  | 5 Kilometres of bulk lines constructed in Bergville Phase 1 by 30/06/2020 | 5 Kilometres of bulk lines constructed in Bergville Phase 1 by 30/06/2020 | New Indicator | New Indicator | 1,25Kilometres of bulk lines constructed in Bergville Phase 2 by 30/06/2019 | 1,25Kilometres of bulk lines constructed in Bergville Phase 2 by 30/06/2019 | 1,25Kilometres of bulk lines constructed in Bergville Sanitation Phase 2 by 31/12/2019 | 18,6 Kilometres of bulk lines constructed in Bergville Sanitation Phase 2 by 31/12/2019 | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
[6 empty] | 4 km's of Raw Water Bulk Line constructed at Kwanobamba Ezitendeni BulkWater Supply by 30 June 2020 | 4 km's of Raw Water Bulk Line constructed at Kwanobamba Ezitendeni BulkWater Supply by 30 June 2020 | New Indicator | New Indicator | n/a | n/a | 500 Meters of Raw Water Bulk Line constructed at Kwanobamba Ezitendeni BulkWater Supply by 31/12/2019 | 0 Meters of Raw Water Bulk Line constructed at Kwanobamba Ezitendeni BulkWater Supply by 31/12/2019 | Not Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
[6 empty] | 4 Kilometers of Supply Bulk Line at Ekuvukeni Water by 30/06/2020 | 4 Kilometers of Supply Bulk Line at Ekuvukeni Water by 30/06/2020 | New Indicator | New Indicator | 1,25 Kilometers of Supply Bulk Line at Ekuvukeni Water by 30/06/2019 | 1,25 Kilometers of Supply Bulk Line at Ekuvukeni Water by 30/06/2019 | 1,25 Kilometers of Supply Bulk Line at Ekuvukeni Water by 31/12/2019 | 1,25 Kilometers of Supply Bulk Line at Ekuvukeni Water by 31/12/2019 | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD04 |  | Provide Community with sanitation Supply | Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | Kilometres |  | 27,2Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | New Indicator | New Indicator | 6,3Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | 6,3Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | 9,7Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | 9,7Km's of Sewer Reticulation Lines Constructed at Bergville Sanitation Project | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD05 |  | Provide community water supply | Date of Completion of Design Development for Umtshezi East Water Supply | Date |  | Date of Completion of Design Development for Umtshezi East Water Supply | Completion of Designs at Umtshezi East Bulk Water by 31/12/2019 | New Indicator | New Indicator | n/a | n/a | Completion of Designs at Umtshezi East Bulk Water by 31/12/2019 | Completion of Designs at Umtshezi East Bulk Water by 31/12/2019 | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD06 |  |  | No of 100 kilo liters of Resevour constructed at Oliphantsskop Water Traetments Works by 30/06/2020 | Number |  | One(1) of 100kilo liters of Resevour constructed at Oliphantsskop Water Traetments Works by 30/06/2020 | One(1) of 100kilo liters of Resevour constructed at Oliphantsskop Water Traetments Works by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD07 |  |  | Number of standpipes constructed a Fitty Park Water Supply Scheme by 30/06/2020 | Number |  | 180 standpipes constructed a Fitty Park Water Supply Scheme by 30/06/2020 | New Indicator | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
WSIG
BSD08 | To provide infrastructure and sustainable basic services | Provide community water supply | Date of completion Moyeni Zwelisha Design Document | Date |  | Completion Moyeni Zwelisha Design Document by 30/06/2020 | Completion Moyeni Zwelisha Design Document by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | n/a | n/a |  | Water,Sanitation and Technical Services | WSIG ALLOCATION | Signed Engineers Report
BSD09 |  |  | km of Estcourt Industrial Pipeline constructed at Escourt by 30/06/2020 | Kilometers |  | 11.89 km of Estcourt Industrial Pipeline constructed at Escourt by 30/06/2020 | New Indicator | New Indicator | New Indicator | 2,7 km of Estcourt Industrial Pipeline constructed at Escourt by 30/09/2019 | 0 km of Estcourt Industrial Pipeline constructed at Escourt by 30/06/2020 | 4,69 km of Estcourt Industrial Pipeline constructed at Escourt by 30/06/2020 | 4,3 km of Estcourt Industrial Pipeline constructed at Escourt by 30/06/2020 | Not Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD10 |  |  | Kilometers of bulk pipelines upgrded at Wembezi WCDM by 30/06/2020 | Kilometer |  | 13,1 bulk pipelines upgrded at Wembezi WCDM by 30/06/2020 | New Indicator | New Indicator | New Indicator | 1 Kilometers bulk pipelines upgrded at Wembezi WCDM by 30/09/2019 | 0 Kilometers bulk pipelines upgrded at Wembezi WCDM by 30/06/2020 | 1,1 kilometers bulk pipelines upgrded at Wembezi WCDM by 31/12/2019 | 0 kilometers bulk pipelines upgrded at Wembezi WCDM by 31/12/2019 | Not Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD11 |  |  | Kilometer of reticulation pipelines constructed at WSIG related projects by 30/06/2020 (Ennersdale- Ephangwini phase 3,Ennersdale-Ephangwini phase 4) | Kilometer |  | 24.8 Kilometer of reticulation pipelines constructed at Ennersdale- Ephangwini phase 3 by 30/06/2020 | 24.8 Kilometer of reticulation pipelines constructed at Ennersdale- Ephangwini phase 3 by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | 3,3Kilometer of reticulation pipelines constructed at Ennersdale- Ephangwini phase 3 by 31/12/2019 | 3,3Kilometer of reticulation pipelines constructed at Ennersdale- Ephangwini phase 3 by 31/12/2019 | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
[6 empty] | 29.1 reticulation pipelines constructed at Ennersdale-Ephangwini phase 4 by 30/06/2020 | 29.1 reticulation pipelines constructed at Ennersdale-Ephangwini phase 4 by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | 4.7 reticulation pipelines constructed at Ennersdale-Ephangwini phase 4 by 31/12/2019 | 4.7 reticulation pipelines constructed at Ennersdale-Ephangwini phase 4 by 31/12/2019 | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD12 | To eradicate water backlogs within a district | Provide portable water to households | Number of yard connections constructed in WSIG related projects by 30/06/2020( Ennersdale-Ephangwini Phase 3,Ennersdale-Ephangwini Phase 4) | Number |  | 300 yard connections in Ennersdale-Ephangwini Phase 3 by 30/06/2020 | 300 yard connections in Ennersdale-Ephangwini Phase 3 by 30/06/2020 | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
[6 empty] | 250 yard connections in Ennersdale-Ephangwini Phase 4 by 30/06/2020 |  | New Indicator | New Indicator | n/a | n/a | n/a | n/a | n/a | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD13 |  |  | Number district wide springs protected by 30/06/2020 | Number | Various | 10 district wide springs protected by 30/06/2020 | 42 district wide spring protected by 30/06/2020 | 37 district wide springs protected by 30/06/2019 | 10 district wide spring to protected by 30/06/2020 | n/a | n/a | 10 district wide springs protected by 31/12/2020 | 10 district wide springs protected by 31/12/2019 | Achieved | Water,Sanitation and Technical Services |  | Signed Engineers Report
BSD14 | To ensure safe and healthy potable water | Implement an effective water and waste water monitoring program | Number of water treatment plants monitred by 30/06/2020 | Number | Various | Forteen (14) water treatment plants monitored by 30/06/2020 | Forteen (14) water treatment plants monitored by 30/06/2019 | Forteen (14) water treatment plants monitored by 30/06/2018 | n/a | Forteen (14) water treatment plants monitored by 31/08/2019 | Forteen (14) water treatment plants monitored by 31/08/2019 | Forteen (14) water treatment plants monitored by 31/12/2019 | Forteen (14) water treatment plants monitored by 31/12/2019 | Achieved | Municipal Health and Water Service Authority | OPEX | Signed reports
BSD15 |  |  | Number of waste water treatment works monitored by 30/06/2020 | Number | Various | Nine (9) waste water treatment works monitored by 30/06/2020 | Nine (9) waste water treatment works monitored by 30/06/2019 | Nine (9) waste water treatment works monitored by 30/06/2018 | n/a | Nine (9) waste water treatment works monitored by 31/08/2019 | Nine (9) waste water treatment works monitored by 31/08/2019 | Nine (9) waste water treatment works monitored by 31/12/2019 | Nine (9) waste water treatment works monitored by 31/12/2019 | Achieved | Municipal Health and Water Service Authority | OPEX | Signed reports
BSD16 |  | Monitor food selling outlets compliance | Number of food handling premises inspected by 30/06/2020 | Number | All | Eight Hundred and Sixty Four (864) food handling premises inspected by 30/06/2020 | One Thousand and Eight (1008) food handling premises inspected by 30/06/2019 | One Thousand and Eight (1008) food handling premises inspected by 30/06/2018 | n/a | 216 formal food handling premises inspected by 31/08/2019 | 216 formal food handling premises inspected by 31/08/2019 | 216 formal food handling premises inspected by 31/12/2019 | 216 formal food handling premises inspected by 31/12/2019 | Achieved | Municipal Health and Water Service Authority | OPEX | Signed reports
KPA3: LOCAL ECONOMIC DEVELOPMENT
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | INDICATORS | Unit of Measure | Ward No. | ANNUAL TARGET | 2018/19 |  |  | Q1 | Q1 Actual | Q2 | Q2 Actual | Achieved/Not Achieved | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog | Projected Target |  | Projected Target
LED01 | To Increase Job opportunities | Creation of job opportunities | Number of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2020 | Number | District -wide | 432 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2020 | 3200 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2020 | 1053 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2019 | 2147 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | Water, Sanitation & Technical Services/Social & Economic Services | EPWP Grant | Signed reports
LED02 | To enhance the Uthukela Local Economic Development | LED policy reviewed | Date of review and adoption of LED strategy by Council 30/06/2020 | Date | District -wide | Review and adoption of LED strategy by Council by 30/06/2020 | Review and adoption of LED strategy by Council by 30/06/2020 | Review and adoption of LED strategy by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | n/a | Social and Economic Services | OPEX | Council Resolution and LED strategy
LED03 | To improve intergovernmental relations | Convene district LED/Tourism Forum meetings | Number of fucntional disrtict LED/Tourism forums 30/06/2019 | Number | n/a | One (1) fucntional district LED/Tourism and planning forum by 30/06/2019 | One (1) fucntional district LED/Tourism and planning forum by 30/06/2019 | One (1) fucntional district LED/Tourism and planning forum by 30/06/2018 | n/a | One (1) fucntional district LED/Tourism and planning forum by 30/09/2019 | One (1) fucntional district LED/Tourism and planning forum held on the 30/09/2019 | One (1) fucntional district LED/Tourism and planning forum by 31/12/2019 | One (1) fucntional district LED/Tourism and planning forum held on the 31/12/2019 | Achieved | Social and Economic Services | OPEX | Signed reports
KPA 4: GOOD GOVERNANCE & PUBLIC PARTICIPATION
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | INDICATORS | Unit of Measure | Ward No. | ANNUAL TARGET | 2018/19 |  |  | Q1 | Q1 Actual | Q2 | Q2 Actual | Achieved/Not Achieved | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
GGPP01 | To ensure good and effective governance | Participate the IGR Structures | Percentage of IGR Structures meetings coordinated by 30/06/2020 | Percentage | n/a | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2020 | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2020 | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2020 | n/a | Hundred (100%) of IGR Structures meetings coordinated by 31/09/2019 | Hundred (100%) of IGR Structures meetings coordinated by 31/09/2019 | Hundred (100%) of IGR Structures meetings coordinated by 31/12/2019 | Eighty (80%) of IGR Structures meetings coordinated by 31/12/2019 | Not Achieved | Corporate Services | OPEX | Notice, minutes & attendance registers
GGPP02 | To promote the interest of designated groups | Participate in the annual programmes | Number of Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2020 | Number | All | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2020 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2020 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2019 | n/a | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/09/2019 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/09/2019 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 31/12/2019 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 31/12/2019 | Achieved | Office of the MM | OPEX | Signed Reports
KP5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | INDICATORS | Unit of Measure | Ward No. | ANNUAL TARGET | 2018/19 |  |  | Q1 | Q1 Actual | Q2 | Q2 Actual | Achieved/Not Achieved | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog | Projected Target |  | Projected Target
MFVM01 | To ensure legally sound financial viability and management | Timeous financial reporting and management | Percentange of MIG Expenditure by 30/06/2020 | Percentage | n/a | Hundred (100%) of MIG expenditure by 30/06/2020 | Hundred (100%) of MIG expenditure by 30/06/2020 | n/a | Hundred (100%) of MIG expenditure by 30/06/2019 | Seventy (25%) of MIG expenditure by 31/03/2019 |  | Seventy (50%) of MIG expenditure by 31/03/2019 |  |  | Water, Sanitation & Technical Services | MIG | Grant exenditure report and proof of payments
MFVM02 |  |  | Percentange of annual allocation to free basic services spent by 30/06/2020 | Percentage | n/a | Hundred (100%) of annual allocation to free basic services spent by 30/06/2020 | Hundred (100%) of annual allocation to free basic services spent by 30/06/2020 | n/a | Hundred (100%) of annual allocation to free basic services spent by 30/06/2019 | Twenty Five (25%) of annual allocation to free basic services spent by 31/09/2019 | None as Free basic services were not budgeted for in the current year | Fifty (50%) of annual allocation to free basic services spent by 31/12/2019 | None as Free basic services were not budgeted for in the current year | Not Achieved | Budget & Treasury Office | OPEX | Signed reports
MFVM03 |  |  | Percentage of operating budget spent by 30/06/2020 | Percentage | n/a | Hundred (100%) of operating budget spent by 30/06/2020 | Hundred (100%) of operating budget spent by 30/06/2020 | n/a | Hundred (100%) of operating budget spent by 30/06/2019 | Twenty Five (25%) of operating budget spent by 30/09/2019 | 70,41% of operating budget spent by 30/09/2019 | Fifty (50%) of operating budget spent by 31/12/2019 | Thirty Six point Nine (36.9%)of operating budget spent by 31/12/2019 | Not Achieved | Budget & Treasury Office | OPEX | Signed reports
MFVM04 |  |  | Percentange of capital budget spent by 30/06/2020 | Percentage | n/a | Hundred (100%) of capital budget spent by 30/06/2020 | Hundred (100%) of capital budget spent by 30/06/2020 | n/a | Hundred (100%) of capital budget spent by 30/06/2019 | Twenty Five (25%) of capital budget spent by 30/09/2019 | 90,49 of capital budget spent by 30/09/2019 | Fifty (50%) of capital budget spent by 31/12/2019 | Thirty Eight (38%) of capital budget spent by 31/12/2019 | Not Achieved | Budget & Treasury Office | CAPEX | Signed reports
MFVM05 |  |  | Percentange of repairs and maintenance spent by 30/06/2020 | Percentage | n/a | Hundred (100%) of repairs and maintenance spent by 30/06/2020 | Hundred (100%) of repairs and maintenance spent by 30/06/2020 | n/a | Hundred (100%) of repairs and maintenance spent by 30/06/2019 | Twenty Five (25%) of repairs and maintanance budget spent by 30/09/2019 | 20% of repairs and maintanance budget spent by 30/09/2019 | Fifty (50%) of repairs and maintanance budget spent by 30/09/2019 | 15.54% of repairs and maintanance budget spent by 31/12/2019 | Not Achieved | Budget & Treasury Office | OPEX | Signed reports
MFVM06 |  |  | Ratio on financial viability in terms of debt coverage by 30/06/2020 | Ratio | n/a | 1:03 | 1:03 | 1:03 | 1:03 | 1:03 | 1, 09: 03 | 1:03 | 1, 09: 03 | Achieved | Budget & Treasury Office | OPEX | Signed reports
MFVM07 |  |  | Ratio on financial viability in terms of cost coverage by 30/06/2020 | Ratio | n/a | 1:02 | 1:02 | 1:02 | 1:02 | 1:02 | 0,52 : 02 | 1:02 | 0,52 : 02 | Not Achieved | Budget & Treasury Office | OPEX | Signed reports
MFVM08 |  |  | Ratio on financial viability in terms of outstanding service debtors to revenue by 30/06/2020 | Ratio | n/a | 1:01 | 1:01 | 1:01 | 1:01 | 1:01 | 2,1 : 01 | 1:01 | 2,1 : 01 | Achieved | Budget & Treasury Office | OPEX | Signed reports
MFVM09 |  |  | Date of approval of 2020/21 budget by 31/05/2020 | Date | n/a | Approval of 2020/21 budget by 31/05/2020 | Approval of 2020/21 budget by 31/05/2020 | Approval of 2019/20 budget by 31/05/2019 | n/a | n/a | n/a | n/a | n/a | n/a | Budget & Treasury Office | OPEX | Council resolution
MFVM10 |  |  | Date of submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2019 | Date | n/a | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2019 | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2019 | Credble 2016/17 Annual Financial Statements submitted to the Auditor-Genral by 31/08/2017 | n/a | 2018/19 Annual Financial Statements submitted to the Auditor-Genral by 31/08/2019 | 2018/19 Annual Financial Statements submitted were submitted to the Auditor-Genral on the 31/08/2019 | n/a | n/a | n/a | Budget & Treasury Office | OPEX | Proof of submission and Annual Financial Statements
MFVM11 |  |  | Percentange of functional bid committees by 30/06/2020 | Percentage | n/a | Hundred (100%) of functional bid committees by 30/06/2020 | Hundred (100%) of functional bid committees by 30/06/2019 | Hundred (100%) of functional bid committees by 30/06/2018 | n/a | Hundred (100%) of functional bid committees by 30/09/2019 | Hundred (100%) of functional bid committees by 30/09/2019 | Hundred (100%) of functional bid committees by 31/12/2019 | Hundred (100%) of bid committees were functional by 31/12/2019 | Achived | Budget & Treasury Office | OPEX | SCM reports
MFVM12 | To improve audit opinion | Implement an audit action plan | Percentage of audit queries raised by the Auditor-General addressed by 30/06/2020 | Percentage | n/a | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/06/2020 | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/06/2019 | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/06/2018 | n/a | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/09/2019 | Nighty (90%) of audit queries raised by the Auditor-General addressed by 30/09/2019 | n/a | n/a | n/a | All Departments | OPEX | Audit action plan and dashboard report
KPA 6: CROSS CUTTING ISSUES
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | INDICATORS | Unit of Measure | Ward No. | ANNUAL TARGET | 2018/19 |  |  | Q1 | Q1 Actual | Q2 | Q2 Actual | Achieved/Not Achieved | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog | Projected Target |  | Projected Target
CCI01 | To improved implementation of policies and by-laws | Adopted estates bylaws | Number of by-laws reviewed and adopted by Council by 30/06/2020 | Number | All | Seven (7) by-laws reviewed and adopted by Council by 30/06/2020 | Seven (7) by-laws reviewed and adopted by Council by 30/06/2019 | n/a | Seven (7) by-laws reviewed and adopted by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | Corporate Services | OPEX | Council resolutions, copies of advertisements and copy of the by-law document
CCI02 | Efficient & Credible Stratgic & Spatial Municipal Planning | Revision of a Credible Intergrated Development Plan | Date of review and adoption of credible integrated development planning by Council by 31/05/2020 | Date | n/a | Review and adoption of credible integrated development planning by Council by 31/05/2020 | Review and adoption of credible integrated development planning by Council by 30/06/2019 | Credible integrated development planning reviewed and adopted by Council by 31/05/2018 | n/a | n/a | n/a | n/a | n/a | n/a | Office of the MM | OPEX | Council resolution and Integrated development plan
CCI03 | To ensure the implementation of Spatial Development Framework | Improved Spatial Development Framework | Date of review and adoption of district Spatial Development framework by Council by 30/06/2020 | Date | n/a | Review and adoption of district Spatial Development framework by Council by 30/06/2020 | Review and adoption of district Spatial Development framework by Council by 30/06/2019 | n/a | Review and adoption of district Spatial Development framework by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | Social and Economic Services | OPEX | Council resolution and Spatial Development framework
CCI04 | To insure improved response to Disasters | Establishment of Disaster Management Structures & Systems | Date of review and adoption of Disaster Management Plan by Council by 30/06/2020 | Date | All | Date of review and adoption of Disaster Management Plan by Council by 30/06/2020 | Review and adoption of Disaster Management Plan by Council by 30/06/2019 | n/a | Review and adoption of Disaster Management Plan by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | Social and Economic Services | OPEX | Council Resolution and Disaster Management Plan
CCI05 | To ensure sustainable protection and development of the environment | Development and implementation of environmental management Plan | Date of review and adotion of Environmental Management Plan provided by Council by 30/06/2020 | Date | All | Date of review and adotion of Environmental Management Plan provided by Council by 30/06/2020 | Review and adotion of Environmental Management Plan provided by Council by 30/06/2019 | n/a | Review and adotion of Environmental Management Plan provided by Council by 30/06/2019 | n/a | n/a | n/a | n/a | n/a | Social and Economic Services | OPEX | Council Resolution and Environmental Management Plan