## 24_25 SDBIP
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP): 2024/2025
NAME OF MUNICIPALITY: UTHUKELA DISTRICT MUNICIPALITY | [18 empty] | FINANCIAL YEAR ENDED: 30 JUNE 2025
IDP / SDBIP NO. | Objective | Strategy | Indicator No. | Key Performance Indicator | KPI Measurement | Ward No. | Baseline:2023/2024 |  | 2024/2025 Projections | [9 empty] | Responsible Department | Budget | Portfolio of Evidence
[7 empty] | Annual Target | Annual Actual | Annual Target | Quarter 1 | Quarter 1 Actual | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 2 Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure
KPA 1: MUNICIPAL TRANFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID01 | To ensure a functional Performance Management System | Implementation of PMS Policy & Framework | 1 | Date of adoption Performance Management System by Council by 30/06/2025 | Date of adoption | n/a | Adoption of Performance Management System by Council by 30/05/2024 | Adoption of Performance Management System by Council by 30/05/2024 | Adoption of Performance Management System by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Adoption of Performance Management System by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution, PMS Policy,Framework and Standard Operating Procedures
MTID02 |  |  | 2 | Number of quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2025 | Number of reports | n/a | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2025 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 30/09/2024 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 30/09/2024 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/12/2024 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/03/2025 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 30/06/2025 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/12/2024 | Achieved | N/A | N/A | All Departments | OPEX | Signed copies of reports & Aknowledgement letters
MTID03 |  |  | 3 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2025 | Date of submission | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2024 | Mid-Year Performance Report to the Mayor and Treasuries on the 24/01/2024 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2025 | N/A | N/A | N/A | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2025 | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Proof of submission and Mid-Year Performance Report
MTID04 |  |  | 4 | Date of submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2024 | Date of submission | n/a | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2022 | Unaudited Annual Performance Report submitted to the Auditor-General on the 31/10/2022 | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2024 | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2024 | The unaudited Annual Performance Report to the Auditor-General was submitted to the Auditor General on the 31/08/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Proof of submission and copy of the Annual Performance Report
MTID05 |  |  | 5 | Date of tabling of Annual Report to Council by 31/03/2025 | Date of tabling | n/a | Adoption of Annual Report by Council by 31/03/2024 | Annual Report adopted by Council on 30/04/2024 | Tabling of Annual Report to Council by 31/03/2025 | N/A | N/A | N/A | Tabling of Annual Report to Council by 31/03/2025 | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution
MTID06 |  |  | 6 | Number of formal section 54/56 managers performance reviews conducted by Performance Review Panels by 30/06/2025 | Number of formal reviews | n/a | Two (2) formal section 54/56 managers' performance reviews conducted by 30/06/2024 | Two (2) formal section 45/56 managers' performance reviews conducted by 30/06/2024 | Two (2) formal section 54/56 managers' performance reviews conducted by Performance Review Panels by 30/06/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Signed Assessment Reports
MTID07 | To ensure fucntional risk and compliance management | Review and adopt risk and compliance governance policies | 7 | Number of risk and Compliance governance Policies adopted by Council by 30/06/2025 | Date of review | n/a | Review and adoption of risk management framework by Council by 30/06/2024 | Risk management framework reviewed and adopted by Council on the 26/06/2024 | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution and Policies
MTID08 |  | Ensure functionality of Risk Management Committee | 8 | Number of Risk Committee meetings held by 30 June 2025 | Number meetings | n/a | Four (4) Risk Committee meetings held by 30 June 2024 | Four (4) Risk Committee meetings held by 30 June 2024 | Four (4) Risk Committee meetings held by 30 June 2025 | One (1) Risk Committee meetings held by 30/09/2024 | One (1) Risk Committee meetings held by 30/09/2024 | One (1) Risk Committee meetings held by 31 December 2024 | One (1) Risk Committee meetings held by 31 March 2025 | One (1) Risk Committee meetings held by 30 June 2025 | One (1) Risk Committee meetings held by 31 December 2024 | Achieved | N/A | N/A | Office of the MM | OPEX | Notice,Agenda, Attandance Register, Minutes
MTID09 | To Improve organisational Capacity | Review of organisational structure | 9 | Date of organizational structure reviewed and adopted by Council by 31/05/2025 | Date of review and adoption | n/a | Review and adoption of organizational structure by Council by 30/06/2024 | Organizational structure reviewed and adopted by Council by 28/05/2024 | Review and adoption of organizational structure by Council by 31/05/2025 | N/A | N/A | N/A | N/A | Review and adoption of organizational structure by Council by 31/05/2025 | N/A | N/A | N/A | N/A | Corporate Services | OPEX | Council Resolution
MTID10 |  | Ensure implementation of Employment equity plan | 10 | Number of people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2025 | Number of people | n/a | 2 people from employment equity target groups employed in the three (3)highest levels of management in compliance with approved equity plan by 30/06/2024 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2024 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2025 | N/A | N/A | N/A | N/A | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2025 | N/A | N/A | N/A | N/A | Corporate Services | OPEX | Employment Equity Plan and appointment letters
MTID11 |  | Implementation of Workplace Skills Plan | 11 | Percentage of budget spent in the implementation of Workplace Skills Plan by 30/06/2025 | Percentage of budget spent | n/a | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | Fifty Five (55%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2025 | Twenty (25%) of budget spent in the implementation of Workplace Skills Plan by 30/09/2024 | Twenty Six (26%) of budget spent in the implementation of Workplace Skills Plan by 30/09/2024 | Fifty (50%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2024 | Seventy Five (75%) of budget spent in the implementation of Workplace Skills Plan by 31/03/2025 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2025 | Forty Two percent (42%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2024 | Not Achieved | Training have been conducted but payments are pending authorization | Payments will be effected on time to ensure that Target is met. | Corporate Services | OPEX | Financial System Print Out
MTID12 |  |  | 12 | Number of training reports submitted to Council by 30/06/2025 | Number of training reports | n/a | 4 Training reports submitted to Council by 30/06/2024 | 4 Training reports submitted to Council by 30/06/2024 | 4 Training reports submitted to Council by 30/06/2025 | 1 Training report submitted to Council by 30/09/2024 | 1 Training report submitted to Council by 30/09/2024 | 1 Training report submitted to Council by 31/12/2024 | 1 Training report submitted to Council by 31/03/2025 | 1 Training report submitted to Council by 30/06/2025 | 1 Training report submitted to council by 31/12/2024 | Achieved | N/A | N/A | Corporate Services | OPEX | Signed Reports to Council
MTID13 | To ensure an effective and efficient HR systems that addresses Human resources within the municipality | Review and adoption of HR related policies | 13 | Date to review and adopt HR related policies by Council by 30/06/2025 | Date of review and adoption | n/a | Review and adoption of HR related policies by Council by 30/06/2024 | HR related policies reviewed and adopted by Council on the 28/05/2024 | Review and adopt HR related policies by Council by 30/06/2025 | N/A | N/A | N/A | Review and adopt HR related policies by Council by 30/06/2025 | n/a | N/A | N/A | N/A | N/A | Corporate Services | OPEX | HR related policies & Council Resolution
MTID14 | To improve Information and Communication Technology through implementation of ICT policies | Development and review of ICT policies | 14 | Number of ICT Policies developed and reviewed by the Council by the 30th June 2025 | Number of Policies | n/a | Ten (10) ICT Policy reviewed by Council by 30/06/2024 | Ten (10) ICT Policy reviewed by Council by 30/06/2024 | Ten (10) ICT Policy reviewed by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Ten (10) ICT Policy reviewed by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Corporate Services | OPEX | Council Resolution,ICT Plicies
MTID15 | Ensure an effective and functional Fleet Services | Conducting Comprehensive reporting of Fleet Management Services | 15 | Number of Comprehensive Fleet Reports submitted to Council by 30/06/2025 | Number of reports | n/a | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2025 | One (1) of Comprehensive Fleet Reports submitted to Council by 30/09/2024 | 1 Comprehensive Fleet Report submitted to Portfolio and Exco only | One (1) of Comprehensive Fleet Reports submitted to Council by 31/12/2024 | One(1) of Comprehensive Fleet Reports submitted to Council by 31/03/2025 | One (1) of Comprehensive Fleet Reports submitted to Council by 20/06/2025 | One(1) Comprehensive Fleet Report submitted to Council on the 29/11/2024 | Achieved | N/A | N/A | Corporate Services | OPEX | Signed Reports
MTID16 | To ensure effective and efficient internal and external communication strategy. | Review and impelemtation of adopted Communication Strategy | 16 | Date of review and adoption of communication strategy by Council by 30/06/2025 | Date of review and adoption | n/a | Review and adotion of communication strategy by Councl by 30/06/2024 | Communication strategy was reviewed and adopted by Council on 26/06/2024 | Review and adoption of communication strategy by Councl by 30/06/2025 | N/A | N/A | N/A | N/A | Review and adoption of communication strategy by Councl by 30/06/2025 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Communication Strategy & Council Resolution
MTID17 | Improve communications with external Stakeholders | Development of Municipal Communication Strategy | 17 | Number of Municipal Newsletters published for each financial year by 30 June 2025 | Number of Newsletters | n/a | Four (4) Municipal newsletters published by 30/06/2024 | Four (4) Municipal newsletters published by 30/06/2024 | Four (4) Municipal newsletters published by 30/06/2025 | One (1) Municipal newsletters published by 30/09/2024 | One (1) Municipal newsletters published by 30/09/2024 | One (1) Municipal newsletters published by 31/12/2024 | One (1) Municipal newsletters published by 31/03/2025 | One (1) Municipal newsletters published by 30/06/2025 | One (1) Municipal newsletters published by 31/12/2024 | Achieved | N/A | N/A | Office of the MM |  | Municipal newsletters,Proof of Publication
MTID18 | To report & monitor Service Delivery | Submission of quarterly reports to COGTA | 18 | Number of Circular 88 reports submitted to Provincial COGTA by 30/06/2025 | Number of reports | n/a | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2024 | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2024 | 4 Circular 88 reports submitted to Provincial COGTA by 30/06/2025 | 1 Circular 88 reports submitted to Provincial COGTA by 30/09/2024 | 1 Circular 88 reports submitted to Provincial COGTA by 30/09/2024 | 1 Circular 88 reports submitted to Provincial COGTA by 31/12/2024 | 1 Circular 88 reports submitted to Provincial COGTA by 31/03/2025 | 1 Circular 88 reports submitted to Provincial COGTA by 30/06/2025 | 1 Circular 88 reports submitted to Provincial COGTA by 31/12/2024 | Achieved | N/A | N/A | Office of the MM | OPEX | Circular 88 reports , Proof of submission
MTID19 | To improve the municipal Audit opinion | Effective Audit and Performance Committee | 19 | Number of Audit and Performance Committee meetings held by 30/06/2025 | Number of meetings | n/a | 4 Audit and Performance Committee meetings held by 30/06/2024 | 4 Audit and Performance Committee meetings held by 30/06/2024 | 4 Audit and Performance Committee meetings held by 30/06/2025 | 1 Audit and Performance Committee meeting held by 30/09/2024 | 3 Audit and Performance Committee meeting held on the 14 August 2024 ;23 August 2024 and 28 August 2024 | 1 Audit and Performance Committee meeting held by 31/12/2024 | 1 Audit and Performance Committee meeting held by 31/03/2025 | 1 Audit and Performance Committee meeting held by 30/06/2025 | 1 Audit and Performance Committee meeting held on the 18/12/2024 | Achieved |  |  | Office of the MM | OPEX | Minutes with attendance registers
MTID20 |  | Oversight meetings held | 20 | Number of MPAC meetings convened by 30/06/2025 | Number of meetings | n/a | 4 MPAC meetings convened by 30/06/2024 | 4 MPAC meetings convened by 30/06/2024 | 4 MPAC meetings convened by 30/06/2025 | 1 MPAC meeting convened by 30/09/2024 | 2 MPAC meeting convened by 07&08 August 2024 | 1 MPAC meeting convened by 31/12/2024 | 1 MPAC meeting convened by 31/03/2025 | MPAC meeting convened by 30/03/2025 | 2 MPAC meeting convened on the 07/10/2024 and 08/10/2024 | Achieved | The 07th October 2024 was for training conducted by KZN COGTA |  | Office of the MM | OPEX | Minutes with attendance registers
KPA2: BASIC SERVICE DELIVERY
BSD01 | To provide infrastructure and sustainable basic services | Provide community water supply | 21 | Number of Households provided with water to eradicate backlog by 30/06/2025 | Number | Various | Four Hundred and Sixty two (462) provided with water to eradicate backlog by 30/06/2024 (95 Loskop 199 Okhahlamba West 168 Okhahlamba East ) | Four Hundred and Sixty two (462) provided with water to eradicate backlog by 30/06/2024 (95 Loskop 199 Okhahlamba West 168 Okhahlamba East ) | 3237 of Households provided with water to eradicate backlock by 30/06/2025 | 100 Households provided with water to eradicate backlock by 31/09/2024 | 0 Households provided with water to eradicate backlock by 31/09/2024 | 1246 Households provided with water to eradicate backlock by 31/12/2024 | 1591 Households provided with water to eradicate backlock by 31/03/2025 | 300 No Household provided with water to eradicate backlock by 30/06/2025 | Zero (0) Households provided with water to eradicate backlock by 31/12/2024 | Not Achieved |  |  | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report, Beneficiary listing and Happy letters
BSD02 |  |  | 22 | Number of sedimentation tank constructed at Bergvile WTW to be completed by 30/09/2024 | Number | 11 | One (1) sedimentation tank constructed at Bergvile WTW to be completed by 30/06/2024 | Zero (0) sedimentation tank constructed at Bergvile WTW to be completed by 30/06/2024 | 1 sedimentation tank to be constructed at Bergville by 30/09/2024 | 1 sedimentation tank to be constructed at Bergville by 30/09/2024 | 1 sedimentation tank to be constructed at Bergville by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | R 20,000,000.00 | Signed Engineers Report
BSD03 |  |  | 23 | Number of backwash filters to be constructed at Bergville WTW by 30/09/2024 | Number | 11 | New Indicator | New Indicator | 4 backwash filters to be constructed at Bergville WTW by 30/09/2024 | 4 backwash filters to be constructed at Bergville WTW by 30/09/2024 | 4 backwash filters to be constructed at Bergville WTW by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD04 |  |  | 24 | Number of Pump station at Bergvile WTW to be completed by 30/09/2024 | Number | 11 | One (1) of Pump station at Bergvile WTW to be completed by 30/06/2024 | One (1) of Pump station at Bergvile WTW to be completed by 30/06/2024 | 2 pumpstation to be constructed at Bergville WTW by 30/09/2024 | 2 pumpstation to be constructed at Bergville WTW by 30/09/2024 | 2 pumpstation to be constructed at Bergville WTW by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD05 |  |  | 25 | Number of bulk pipeline (Rising main from Rose Hill Reservoir to high Tower) constructed at Ezakheni WCDM: Phase 2 by 30/06/2025 | Number | 25 | 0,28 km of bulk pipeline (Rising main from Rose Hill Reservoir to high Tower) constructed at Ezakheni WCDM Phase 2 by 30/06/2024 | 0,28 km of bulk pipeline (Rising main from Rose Hill Reservoir to high Tower) constructed at Ezakheni WCDM Phase 2 by 30/06/2024 | 1,215 KM's of bulk pipeline (Rising main from Rose Hill Reservoir to high Tower) constructed at Ezakheni WCDM: Phase 2 by 30/06/2025 | 0,265 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 30/09/2024 | 1,289km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 30/09/2024 | 0,375 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 31/12/2024 | 0,350 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 31/03/2025 | 0,225 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 30/06/2025 | 0,020 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 31/12/2024 | Not Achieved | Contractor suspended construction work due cashflow problems | Revised program to be submitted by the Contractor | Water, Sanitation & Technical Services | R 20,000,000.00 | Signed Engineers Report
BSD06 |  |  | 26 | Number of Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/06/2025 | Number | 1,2,3,4,5,8,13 & 20 | 07 Bulk meters chamber (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 07 Bulk meters chamber (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 61 Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/06/2025 | 13 Bulk meters to be installed at Ezakheni WCDM: Phase 2 by 31/03/2024 | 0 Bulk meters installed at Ezakheni WCDM: Phase 2 by 31/09/2024 | 18 Bulk meters to be installed at Ezakheni WCDM: Phase 2 by 31/12/2024 | 13 Bulk meters to be installed at Ezakheni WCDM: Phase 2 by 31/03/2025 | 17 bulk meters chambers to be installed at Ezakheni WCDM by 30/06/2025 | (0) Bulk meters installed at Ezakheni WCDM: Phase 2 by 31/12/2024 | Not Achieved | Reprioritizantion of works occurred in the project | Revised program to be submitted by the Contractor | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD07 |  |  | 27 | Kilometres of reticulation (C section subzone-ac pipe replacement) pipeline constructed at Ezakheni WCDM: Phase 2 by 30/06/2025 | Killometres | 1,2,3,4,5,8,13 & 20 | 0,225KM's of reticulation (C section subzone-ac pipe replacement) pipeline to be constructed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 0,225KM's of reticulation (C section subzone-ac pipe replacement) pipeline to be constructed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 5,246 Km's of reticulation(C section subzone-ac replacement )pipelineto be constructed at Ezakheni WCDM: Phase 2 by 30/06/2025 | 2,3 Km's of reticulation(C section subzone-ac replacement )pipeline to be constructed at Ezakheni WCDM: Phase 2 by 30/09/2024 | 3.009 Km's of reticulation(C section subzone-ac replacement )pipeline to be constructed at Ezakheni WCDM: Phase 2 by 30/09/2024 | 1,15 Km's of reticulation(C section subzone-ac replacement )pipeline to be constructed at Ezakheni WCDM: Phase 2 by 31/12/2024 | 1,2 Km's of reticulation(C section subzone-ac replacement )pipeline to be constructed at Ezakheni WCDM: Phase 2 by 31/03/2025 | 0,596 Km's of reticulation(C section subzone-ac replacement )pipeline to be constructed at Ezakheni WCDM: Phase 2 by 30/06/2025 | 0.89 Km's of reticulation(C section subzone-ac replacement )pipeline to be constructed at Ezakheni WCDM: Phase 2 by 31/12/2024 | Not Achieved | Contractor suspended construction work due cashflow problems | Revised program illustrating the planned completion | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD08 |  |  | 28 | Number of Reservoirs to be constructed at Langkloof Package Plant and Bulk Supply: Phase 1 by 30/06/2025 | Number | 1,2,3,4,5,8,13 & 20 | New Indicator | New Indicatorn | 1 Reservoirs to be constructed at Langkloof and Bulk Supply: Phase 1 by 30/06/2025 | 1 Reservoirs to be constructed at Langkloof and Bulk Supply: Phase 1 by 30/09/2024 | 0 Reservoirs to be constructed at Langkloof and Bulk Supply: Phase 1 by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | R 10,833,000.00 | Signed Engineers Report
BSD09 |  |  | 29 | Number of abstraction plant to be installed in Langkloof Package Plant and Bulk Supply by 30/09/2024 | Number | 11 & 12 | New Indicator | New Indicator | One (1) of abstraction plant to be installed in Langkloof Package Plant and Bulk Supply by 30/09/2024 | Number of abstraction plant to be installed in Langkloof Package Plant and Bulk Supply by 30/09/2024 | 0 Number of abstraction plant to be installed in Langkloof Package Plant and Bulk Supply by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD10 |  |  | 30 | Number of kilometres of Reticulation(HDPE Pipeline and PVC Pipeline) constructed at Fitty Park Community water project: Phase 2 by 30/09/2024 | Number | 10 | 13,7 Kilometres of reticulation (HDPE Pipeline and PVC Pipeline) pipelines constructed at Fitty Park Community Water Project by 30/06/2024 | 13,7 Kilometres of reticulation (HDPE Pipeline and PVC Pipeline) pipelines constructed at Fitty Park Community Water Project by 30/06/2024 | 1.222 km of reticulation (HDPE Pipeline and PVC Pipeline)pipeline constructed at Fitty Park Community Water Project by 30/09/2024 | 1.222 km of reticulation (HDPE Pipeline and PVC Pipeline)pipeline constructed at Fitty Park Community Water Project by 30/09/2024 | 1.222 km of reticulation (HDPE Pipeline and PVC Pipeline)pipeline to be constructed at Fitty Park Community Water Project by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | R 10,380,123.27 | Signed Engineers Report
BSD11 |  |  | 31 | Number of VIP toilets constructed by 30/06/2025 | Number | 10 | 2000 VIP toilets constructed by 30/06/2024 | 2000 VIP toilets constructed by 30/06/2024 | 1725 VIP toilets constructed by 30/06/2025 | 710 VIP toilets constructed by 30/09/2024 | 729 VIP toilets constructed by 30/09/2024 | 500 VIP toilets constructed by 31/12/2024 | 250 VIP toilets constructed by 31/03/2025 | 265 VIP toilets constructed by 31/03/2024 | 647 VIP toilets constructed by 31/12/2024 | Achieved | Contractor over achieved due to having multiply subscontractors on site | N/A | Water, Sanitation & Technical Services | R 17,0105,200 | Signed Engineers Report
BSD12 |  |  | 32 | Number of Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 by 30/06/2025 | Number | 4 | New Indicator | New Indicator | 26.4 Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 by 30/06/2025 | 6.6KM of Reticulation pipeline to be constructed at Vimbukhalo 3 by 30/09/2024 | 6.85KM of Reticulation pipeline constructed at Vimbukhalo 3 by 30/09/2024 | 6.6KM of Reticulation pipeline to be constructed at Vimbulayo 3 by 31/12/2024 | 6.6KM of Reticulation pipeline to be constructed at Vimbukhalo 3 by 30/03/2025 | 6.6KM of Reticulation pipeline to be constructed at Vimbukhalo 3by 30/06/2025 | 8.68 KM of Reticulation pipeline constructed at Vimbukhalo 3 by 31/12/2024 | Achieved | Contractor adhered to submittted program and performed exceptional on site | N/A | Water, Sanitation & Technical Services | R 13,190,738.79 | Signed Engineers Report
BSD13 |  |  | 33 | Number of Resevoirs to be constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 by 30/06/2025 | Number | 1 | New Indicator | New Indicator | 1 Resevoirs to be constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 by 30/06/2025 | N/A | N/A | N/A | N/A | 1 Reseivor to be constructed at Vimbukhalo 3 by 30/06/2025 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD14 |  |  | 34 | Number of Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 4 by 30/06/2025 | Number | 1 | New Indicator | New Indicator | 20.0 Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 4 by 30/06/2025 | 5.4KM of Reticulation pipeline to be constructed at Vimbukhalo 4 by 30/09/2024 | 5.55KM of Reticulation pipeline to be constructed at Vimbukhalo 4 by 30/09/2024 | 5.4KM of Reticulation pipeline to be constructed at Vimbukhalo 4by 31/12/2024 | 5.0KM of Reticulation pipeline to be constructed at Vimbukhalo 4 by 30/03/2025 | 4.2KM of Reticulation pipeline to be constructed at Vimbukhalo 4 by 30/06/2025 | 7.45 KM of Reticulation pipeline constructed at Vimbukhalo 4by 31/12/2024 | Achieved | Contractor adhered to submittted program and performed exceptional on site | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD15 | To provide santitation system to the community | Provision and maintainance of sanitation infrastructure | 35 | Number of Resevoirs to be constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 4 by 30/06/2025 | Number | Various | New Indicator | New Indicator | 1 Resevoirs to be constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 4 by 30/06/2025 | N/A | N/A | N/A | N/A | 1 Reseivor to be constructed at Vimbukhalo 4 by 30/06/2025 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD16 |  |  | 36 | Number of bulk pipeline(AC pipeline) constructed at Steadville WCDM by 30/06/2025 | Number | Various | 2,45 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | 2,45 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | 8,029 Number of bulk pipeline(AC pipeline) constructed at Steadville WCDM by 30/06/2025 | 3,65 km of bulk pipeline (AC pipeline) to be constructed at Steadville WCDM by 30/09/2024 | 3,65 km of bulk pipeline (AC pipeline) constructed at Steadville WCDM by 30/09/2024 | 3,45 km of bulk pipeline (AC pipeline) to be constructed at Steadville WCDM by 31/12/2024 | 0,929 km of bulk pipeline (AC pipeline) to constructed at Steadville WCDM by 31/03/2024 | N/A | 0.156 km of bulk pipeline (AC pipeline) constructed at Steadville WCDM by 31/12/2024 | Not Achieved | Contractor suspended construction work due cashflow problems | Revised program to be submitted by the Contractor | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Repor, Beneficiary listing and Happy letters
BSD17 | To provide infrastructure and sustainable basic services | Provide community water supply | 38 | Number of installation of bulk metering chambers at Steadville WCDM by 30/06/2025 | Number | 7 & 28 | (3) installation of bulk metering at Steadville by 30/06/2024 | (3) installation of bulk metering at Steadville by 30/06/2024 | 5 bulk meters chambers to be installed at Steadville WCDM by 30/06/2025 | 4 bulk meters chambers to be installed at Steadville WCDM by 30/09/2024 | 0 bulk meters chambers installed at Steadville WCDM by 30/09/2024 | 1 bulk meters chambers to be installed at Steadville WCDM by 31/12/2024 | N/A | N/A | 1 bulk meters chambers to be installed at Steadville WCDM by 31/12/2024 | Not Achieved | Contractor suspended construction work due cashflow problems | Revised program to be submitted by the Contractor | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD18 |  |  | 39 | Number of bulk pipeline constructed at Ladysmith AC pipeline replacement by 31/03/2025 | Number | Various | 2,45 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | 2,45 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | 3,266 km of bulk pipeline constructed at Ladysmith AC pipeline replacement by 31/03/2025 | 1,516 km of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/09/2024 | 1,966 km of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/09/2024 | 1,25 km of bulk pipeline constructed at Ladysmith AC pipeline replacement by 31/12/2024 | 0,5 km of bulk pipeline to constructed at Ladysmith AC pipeline replacement by 31/03/2025 | N/A | 0.069 km of bulk pipeline constructed at Ladysmith AC pipeline replacement by 31/12/2024 | Not Achieved | Contractor suspended construction work due cashflow problems | Revised program to be submitted by the Contractor | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD19 |  |  | 40 | Number of installation of bulk metering at Ladysmith AC pipeline replacement by 31/12/2024 | Number | 7, 28, 29 & 30 | (3) installation of bulk metering at Ladysmith AC pipeline replacement by 31/03/2024 | (3) installation of bulk metering at Ladysmith AC pipeline replacement by 31/03/2024 | 4 bulk meter chambers to be installed at Ladysmith AC pipeline replacement by 31/12/2024 | 3 bulk meter chambers to be installed at Ladysmith AC pipeline replacement by 30/09/2024 | 0 bulk meter chambers to be installed at Ladysmith AC pipeline replacement by 30/09/2024 | 1 bulk meter chambers to be installed at Ladysmith AC pipeline replacement by 31/12/2024 | N/A | N/A | 0 bulk meter chambers installed at Ladysmith AC pipeline replacement by 31/12/2024 | Not Achieved | Contractor suspended construction work due cashflow problems | Revised program to be submitted by the Contractor | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD20 |  |  | 41 | Number of Earthworks (Wetland portion)completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2024 | Number | 14 | New Indicator | New Indicator | 1 Earthworks (Wetland portion)completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2024 | 1 Earthworks (Wetland portion)completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2025 | 1 Earthworks (Wetland portion)completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD21 |  |  | 42 | Number of Sewer Pump Stations (M&E) completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 30/09/2024 | Number | 14 | Two (2) of Sewer Pump Stations (M&E) completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 30/06/2024 | Two (2) of Sewer Pump Stations (M&E) completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 30/06/2024 | 1 Sewer Pump Station (M&E)to be completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 30/09/2024 | 1 Sewer Pump Station (M&E)to be completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 30/09/2024 | 0 Sewer Pump Station (M&E)to be completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD22 |  |  | 43 | Number of Sedimentation Tank (M&E) completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2024 | Number | 14 | One (1) of Sedimentation Tank (M&E) completed at Kwanobamba/Ezitendeni Sanitation project by 30/06/2024 | One (1) of Sedimentation Tank (M&E) completed at Kwanobamba/Ezitendeni Sanitation project by 30/06/2024 | 2 Sedimentation Tanks (M&E) to be completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2024 | 2 Sedimentation Tanks (M&E) to be completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2024 | 0 Sedimentation Tanks (M&E) completed at Kwanobamba/Ezitendeni Sanitation project by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | R699 1000.00 | Signed Engineers Report
BSD23 |  |  | 44 | Killometres of sewer pipeline constructed at Ezakheni E Sanitation by 30/09/2024 | Killometres | 14 | New Indicator | New Indicator | 0,085 of sewer pipelineline constructed at Ezakheni E by 30/09/2024 | 0,085 of sewer pipelineline constructed at Ezakheni E by 30/09/2024 | 0,085 of sewer pipelineline constructed at Ezakheni E by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  | Signed Engineers Report
BSD24 |  |  | 45 | Construction of New Manholes at Ezakheni E by 30/09/2024 | Number | 14 | New Indicator | New Indicator | Construction of 4 New Manholes at Ezakheni E by 30/09/2024 | Construction of 4 New Manholes at Ezakheni E by 30/09/2024 | Construction of 4 New Manholes at Ezakheni E by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD25 |  |  | 46 | Number of installation of MI GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30/09/2024 | Number | 14 | 1,0 MI GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30/06/2024 | 1,0 MI GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30/06/2024 | Installation of 1 GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30/09/2024 | Installation of 1 GMS Reservoir at Ntabamhlophe Community Water Supply Scheme completed by30/09/2024 | Installation of 0 GMS Reservoir at Ntabamhlophe Community Water Supply Scheme completed by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD26 |  |  | 47 | Number of sludge ponds at Loskop Abstraction WTW by 31/03/2025 | Number | 2,3,14 | New Indicator | New Indicator | 2 sludge ponds at Loskop Abstraction WTW by 31/03/2025 | N/A | O sludge ponds constructed at Loskop Abstraction WTW by 31/03/2025 | N/A | 2 sludge ponds at Loskop Abstraction WTW by 31/03/2025 | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD27 |  |  | 48 | Killometres of bulk pipeline to be constructed at Loskop Abstraction WTW by 31/12/2024 | Killometres | 2,3,14 | 0,14 Kilometres of bulk pipeline at Loskop Abstraction WTW by 30/06/2024 | 0,14 Kilometres of bulk pipeline at Loskop Abstraction WTW by 30/06/2024 | 0,22 KM's of bulk pipeline at Loskop Abstraction WTW by 31/12/2024 | 0,2 KM's of bulk pipeline at Loskop Abstraction WTW by 30/09/2024 | 0,095bKM's of bulk pipeline constructed at Loskop Abstraction WTW by 30/09/2024 | 0,002 KM's of bulk pipeline at Loskop Abstraction WTW by 31/12/2024 | N/A | N/A | 0,079 KM's of bulk pipeline at Loskop Abstraction WTW by 31/12/2024 | Achieved | Contractor adhered to submittted program | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD28 |  |  | 49 | Number of boreholes to be drilled, sitted and tested at Ekuvukeni Groundwater by 30/09/2024 | Number | 2,3 & 14 | New Indicator | New Indicator | 20 boreholes to be sitted,drilled and tested at Ekuvukeni Groundwater by 30/09/2024 | 20 boreholes to be sitted,drilled and tested at Ekuvukeni Groundwater by 30/09/2024 | 11 boreholes sitted,drilled and tested at Ekuvukeni Groundwater by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD29 |  |  | 50 | Number of handpumps to be equipped at Ekuvukeni Groundwater by 31/12/2024 | Number | 2,3 & 14 | New Indicator | New Indicator | 5 handpumps to be at equipped Ekuvukeni Groundwater by 31/12/2024 | 1 handpumps to be at equipped Ekuvukeni Groundwater by 30/09/2024 | 0 handpumps equipped at Ekuvukeni Groundwater by 30/09/2024 | 4 handpumps to be at equipped Ekuvukeni Groundwater by 31/12/2024 | N/A | N/A | 0 handpumps not equipped Ekuvukeni Groundwater by 31/12/2024 | Not Achieved | Delay of water quality results by the Geohydrology specialist .Contractor awaiting for recommendation | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD30 |  |  | 51 | Number of production boreholes to be equipped at Ekuvukeni Groundwater by 31/12/2024 | Number | 2,3 & 14 | New Indicator | New Indicator | 5 production boreholes to be equipped atEkuvukeni Groundwater by 31/12/2024 | 1 production borehole to be equipped atEkuvukeni Groundwater by 30/09/2024 | 1 production borehole equipped atEkuvukeni Groundwater by 30/09/2024 | 4 production boreholes to be equipped atEkuvukeni Groundwater by 31/12/2024 | N/A | N/A | 0 production boreholes not equipped atEkuvukeni Groundwater by 31/12/2024 | Not Achieved | Delay of water quality results by the Geohydrology specialist .Contractor awaiting for recommendation | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD31 |  |  | 52 | Killometres of gravity main to be constructed at Ntabamhlophe Water supply scheme by 30/09/2024 | Killometres | 2,3 & 14 | New Indicator | New Indicator | 1.95km of gravity main to be constructed at Ntabamhlophe Water supply scheme by 30/09/2024 | 1.95km of gravity main to be constructed at Ntabamhlophe Water supply schemet by 30/09/2024 | 0km of gravity main to be constructed at Ntabamhlophe Water supply schemet by 30/09/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | R 4,935,053.47 | Signed Engineers Report
BSD32 |  |  | 53 | Number of production boreholes to be refurbished at Water and Sanitation Refurbishment (District Wide ) Phase 3 Project by 30/06/2025 | Number | 9 & 10 | New Indicator | New Indicator | 30 production boreholes to be refurbished at Water and Sanitation Refurbishment Phase 3 Project by 30/06/2025 | N/A | N/A | N/A | 25 production boreholes to be refurbished at Water and Sanitation Refurbishment Phase 3 Project by 31/03/2025 | 5 production boreholes to be refurbished at Water and Sanitation Refurbishment Phase 3 Project by 30/06/2025 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  | Signed Engineers Report
BSD33 |  |  | 54 | Number of pump stations at Water and Sanitation Refurbishment Phase 3 (District Wide) Project by 30/06/2025 | Number | 9 & 10 | New Indicator | New Indicator | 12 pump stations to be refurbished at Water and Sanitation Refurbishment Phase 3 Project by 30/06/2025 | N/A | N/A | N/A | 6 pump stations to be refurbished at Water and Sanitation Refurbishment Phase 3 Project by 31/03/2025 | 6 pump stations to be refurbished at Water and Sanitation Refurbishment Phase 3 Project by 30/06/2025 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  | Signed Engineers Report
BSD34 | To ensure safe and healthy potable water | Implement an effective water and waste water monitoring program | 55 | Number of water treatment plants monitred by 30/06/2025 | Number | 12 | 15 water treatment plants monitored by 30/06/2024 | 15 water treatment plants monitored by 30/06/2024 | 15 water treatment plants monitored by 30/06/2025 | 15 water treatment plants monitored by 30/09/2024 | 15 water treatment plants monitored by 30/09/2024 | 15 water treatment plants monitored by 31/12/2024 | 15 water treatment plants monitored by 31/03/2025 | 15 water treatment plants monitored by 30/06/2025 | 15 water treatment plants monitored by 31/12/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed reports
BSD35 |  |  | 56 | Number of waste water treatment works monitored by 30/06/2025 | Number | 12 | 9 waste water treatment works monitored by 30/06/2024 | 9 waste water treatment works monitored by 30/06/2024 | 9 waste water treatment works monitored by 30/06/2025 | 9 waste water treatment works monitored by 30/09/2024 | 9 waste water treatment works monitored by 30/09/2024 | 9 waste water treatment works monitored by 31/12/2024 | 9 waste water treatment works monitored by 31/03/2025 | 9 waste water treatment works monitored by 30/06/2025 | 9 waste water treatment works monitored by 31/12/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | OPEX | Signed reports
BSD36 | To enhance consumer protection with sufficient food control | Monitor compliance of food sellling outlets | 57 | Number of food handling premises inspected by 30/06/2025 | Number | 21 | 1118 food handling premises inspected by 30/06/2024 | 1118 food handling premises inspected by 30/06/2024 | 1118 food handling premises inspected by 30/06/2025 | 280 food handling premises inspected by 30/09/2024 | 311 food handling premises inspected by 30/09/2024 | 280 food handling premises inspected by 31/12/2024 | 280 food handling premises inspected by 31/03/2025 | 280food handling premises inspected by 30/06/2025 |  | Not Achieved |  |  | Community Services | OPEX | Signed reports
LOCAL ECONOMIC DEVELOPMENT
LED01 | To Increase Job opportunities | Implement Expanded Public Works Programme (EPWP) | 58 | Number of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2025 | Number of EPWP jobs | Various | 1019 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | 849 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | 1123 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2025 | N/A | N/A | N/A | N/A | 1123 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2025 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | EPWP GRANT | Signed reports
LED02 |  |  | 59 | Number of EPWP reports submitted to the funder by 30/06/2025 | Number of EPWP reports | n/a | 12 EPWP reports submitted to the funder by 30/06/2024 | 12 EPWP reports submitted to the funder by 30/06/2024 | 12 EPWP reports submitted to the funder by 30/06/2025 | 3 EPWP reports submitted to the funder by 30/09/2024 | 3 EPWP reports submitted to the funder by 30/09/2024 | 3 EPWP reports submitted to the funder by 31/12/2024 | 3 EPWP reports submitted to the funder by 31/03/2025 | 3 EPWP reports submitted to the funder by 30/06/2025 | 3 EPWP reports submitted to the funder by 31/12/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | OPEX | Signed reports
LED03 | To enhance the Uthukela Local Economic Development | LED policy reviewed | 60 | Date of review and adoption of LED strategy by Council 30/06/2025 | Date of review | n/a | Review and adoption of LED strategy by Council by 30/06/2024 | LED strategy by Council by 28/05/2024 | Review and adoption of LED strategy by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Review and adoption of LED strategy by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Social and Economic Services | OPEX | Council Resolution and LED strategy
LED04 |  | Convene district LED/Tourism Forum meetings | 61 | Number of disrtict LED/Tourism forums meetings held by 30/06/2025 | Number of meetings | n/a | New Indicator | New Indicator | 4 disrtict LED/Tourism forums meetings held by 30/06/2025 | 1 disrtict LED/Tourism forums meeting held by 30/09/2024 | 1 disrtict LED/Tourism forums meeting held by 30/09/2024 | 1 disrtict LED/Tourism forum meetings held by 31/12/2024 | 1 disrtict LED/Tourism forum meetings held by 31/03/2025 | 1 disrtict LED/Tourism forum meetings held by 30/06/2025 | 1 disrtict LED/Tourism forum meetings held on the 27/11/2024 | Achieved | N/A | N/A | Social and Economic Services | OPEX | Signed reports
LED05 | To Increase Job opportunities | Implement Expanded Public Works Programme (EPWP) | 62 | Number of FTE's created through LED initiatives, including capital projects, by 30/06/2025 | Number | Various | New Indicator | New Indicator | 372 FTE's jobs to be created through LED initiatives, including capital projects, by 30/06/2025 | N/A | N/A | N/A | N/A | 372 FTE's jobs to be created through LED initiatives, including capital projects, by 30/06/2024 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Service | EPWP GRANT | Signed Reports
KPA 4: GOOD GOVERNANCE & PUBLIC PARTICIPATION
GGPP01 | To ensure good and effective governance | Participate the IGR Structures | 63 | Percentage of functional IGR Structures by 30/06/2025 | Percentage of fuctional structures | n/a | 100% of functional IGR Structures by 30/06/2024 | 100% of functional IGR Structures by 30/06/2024 | 100% of functional IGR Structures by 30/06/2025 | 100% of functional IGR Structures by 30/09/2024 | 100% of functional IGR Structures by 30/09/2024 | 100% of functional IGR Structures by 31/12/2024 | 100% of functional IGR Structures by 31/03/2025 | 100% of functional IGR Structures by 30/06/2025 | 100% of functional IGR Structures by 31/12/2024 | Achieved | N/A | N/A | Office of the MM | OPEX | Notice, minutes & attendance registers
GGPP02 | To promote the interest of designated groups | Participate in the annual programmes | 64 | Number of Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2025 | Number of special programmes | n/a | 7 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | 8 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | 7 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2025 | N/A | N/A | N/A | 3 Special Programme targeting designated groups co-ordinated and participating in within the district by 31/03/2025 | 4 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2025 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Signed Reports
KP5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM01 | To ensure legally sound financial viability and management | Timeous financial reporting and management | 65 | Percentange of MIG Expenditure by 30/06/2025 | Percentage of exependiture | n/a | 100% of MIG expenditure by 30/06/2024 | 100% of MIG expenditure by 30/06/2024 | 100% of MIG expenditure by 30/06/2025 | 25% of MIG expenditure by 30/09/2024 | 29% of MIG expenditure by 30/09/2024 | 50% of MIG expenditure by 31/12/2024 | 75% of MIG expenditure by 31/03/2025 | 100% of MIG expenditure by 30/06/2025 | 42% of MIG expenditure spent by 31/12/2024 | Not Achieved | Delays in the payment of MIG Expenditure | Acceleration plan developed | Water, Sanitation & Technical Services | MIG | Grant exenditure report and proof of payments
MFVM02 |  |  | 66 | Percentange of annual allocation to free basic services spent by 30/06/2025 | Percentage spent | n/a | 100% of annual allocation to free basic services spent by 30/06/2024 | 0% of annual allocation to free basic services spent by 30/06/2024 | 100% of annual allocation to free basic services spent by 30/06/2025 | 25% of annual allocation to free basic services spent by 30/09/2024 | 16% of annual allocation to free basic services spent by 30/09/2024 | 50% of annual allocation to free basic services spent by 31/12/2024 | 75% of annual allocation to free basic services spent by 31/03/2025 | 100% of annual allocation to free basic services spent by 30/06/2025 | 43% of annual allocation to free basic services spent by 31/12/2024 | Not Achieved | Unfunded Budget approved by Council | Budget Funding Plan developed and implemented | Budget & Treasury Office | OPEX | Signed reports
MFVM03 |  |  | 67 | Percentage of operating budget spent by 30/06/2025 | Percentage spent | n/a | 100% of operating budget spent by 30/06/2024 | 74% of operating budget spent by 30/06/2024 | 100% of operating budget spent by 30/06/2025 | 25% of operating budget spent by 30/09/2024 | 16% of operating budget spent by 30/09/2024 | 50% of operating budget spent by 31/12/2024 | 75% of operating budget spent by 31/03/2025 | 100% of operating budget spent by 30/06/2025 | 37,2% of operating budget spent by 31/12/2024 | Not Achieved | Unfunded Budget approved by Council | Budget Funding Plan developed and implemented | Budget & Treasury Office | OPEX | Signed reports
MFVM04 |  |  | 68 | Percentange of capital budget spent by 30/06/2025 | Percentage spent | n/a | 100% of capital budget spent by 30/06/2024 | 100% of capital budget spent by 30/06/2024 | 100% of capital budget spent by 30/06/2025 | 25% of capital budget spent by 30/09/2024 | 29% capital budget spent by 30/09/2024 | 50% of capital budget spent by 31/12/2024 | 75% of capital budget spent by 31/03/2025 | 100% of capital budget spent by 30/06/2025 | 37,4% of capital budget spent by 31/12/2024 | Not Achieved | Delays in the payment of MIG Expenditure | Acceleration plan developed | Budget & Treasury Office | CAPEX | Signed reports
MFVM05 |  |  | 69 | Percentange of repairs and maintenance spent by 30/06/2025 | Percentage spent | n/a | 100% of repairs and maintenance spent by 30/06/2024 | 38% of repairs and maintenance spent by 30/06/2011 | 100% of repairs and maintenance spent by 30/06/2025 | 25% of repairs and maintenance spent by 30/09/2024 | 13% of repairs and maintenance spent by 30/09/2024 | 50% of repairs and maintenance spent by 31/12/2024 | 75% of repairs and maintenance spent by 31/03/2025 | 100% of repairs and maintenance spent by 30/06/2025 | 22,3% of repairs and maintenance spent by 31/12/2024 | Not Achieved | Unfunded Budget approved by Council | Budget Funding Plan developed and implemented | Budget & Treasury Office | OPEX | Signed reports
MFVM06 |  |  | 70 | Ratio on financial viability in terms of debt coverage by 30/06/2025 | Ratio | n/a | 1:03 | 8,49: 03 | 1:03 | 1:03 | 15:03 | 1:03 | 1:03 | 1:03 | 0.33:03 | Not Achieved | Low collection rate | Credit control and debt collection policy implemented, revenue enhancement strategy developed | Budget & Treasury Office | OPEX | Signed reports
MFVM07 |  |  | 71 | Ratio on financial viability in terms of cost coverage by 30/06/2025 | Ratio | n/a | 1:02 | 1,47: 02 | 1:02 | 1:02 | 0:05 | 1:02 | 1:02 | 1:02 | 0.17:02 | Not Achieved | Low collection rate | Credit control and debt collection policy implemented, revenue enhancement strategy developed | Budget & Treasury Office | OPEX | Signed reports
MFVM08 |  |  | 72 | Ratio on financial viability in terms of outstanding service debtors to revenue by 30/06/2025 | Ratio | n/a | 1:01 | 0,14: 01 | 1:01 | 1:01 | 1.3757 | 1:01 | 1:01 | 1:01 | 14:01 | Not Achieved | Low collection rate | Credit control and debt collection policy implemented, revenue enhancement strategy developed | Budget & Treasury Office | OPEX | Signed reports
MFVM09 |  |  | 73 | Date of approval of 2025/2025 budget by 31/05/2025 | Date of approval | n/a | Approval of 2024/24 budget by 31/05/2022 | 2024/24 Budget was approved on the 28/05/2022 | Approval of 2025/25 budget by 31/05/2025 | N/A | N/A | N/A | N/A | Approval of 2025/25 budget by 31/05/2025 | n/a | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Council resolution
MFVM10 |  |  | 74 | Number of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2025 | Number |  | New Indicator | New Indicator | Twelve (12) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2025 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 September 2024 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 September 2024 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2024 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 March 2025 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2025 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2024 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | Progress Reports, Proof of Submission to Treasury
MFVM11 |  |  | 75 | Date of submission of credible Annual Financial Statements to the Auditor-General by 31/08/2024 | Date of submission | n/a | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2022 | Submitted credible Annual Financial Statements to the Auditor-Genral by 31/10/2022 | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2024 | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2024 | The credible Annual Financial Statements to the Auditor-Genaral on the 31/08/2024 | N/A | N/A | N/A | n/a | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Proof of submission and Annual Financial Statements
MFVM12 |  | Ensure legislative compliance | 76 | Number of Asset Register developed by 30/06/2025 | Number of registers | n/a | 1 Asset Register developed by 30/06/2024 | 1 Asset Register developed by 30/06/2024 | 1Asset Register developed by 30/06/2025 | N/A | N/A | N/A | N/A | 1Asset Register developed by 30/06/2025 | n/a | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Asset Register
MFVM13 |  |  | 77 | Date of adoption of Finance related policies by Council by 31/05/2025 | Date of adoption | n/a | Adoption of Finance related policies by Council 31/05/2024 | Adoption of Finance related policies by Council 31/05/2024 | Adoption of Finance related policies by Council 31/05/2025 | N/A | N/A | N/A | N/A | Adoption of Finance related policies by Council 31/05/2025 | n/a | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Council Resolution
MFVM14 |  | Monitor the compliance with relevant legislation regarding financial expenditure | 78 | Percentage of reduction of Unauthorised, Irregular, Fruitless and Wasteful Expenditure by 30/06/2025 | Percentage of reduction | n/a | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2025 | 2% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/09/2024 | 60% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/09/2024 | 5% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2024 | 8% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/03/2025 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2025 |  | Achieved | N/A | N/A | All Departments | OPEX | Signed Reports to Council
MFVM15 |  |  | 79 | Number of Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2025 | Number | n/a | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2024 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2024 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2025 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/09/2024 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/09/2024 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2024 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/03/2025 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/06/2025 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2024 | Achieved | N/A | N/A | All Departments | OPEX | Signed Reports to Council
MFVM16 | To improve audit opinion | Implement an audit action plan | 80 | Percentage of audit queries raised by the Auditor-General addressed by 30/06/2025 | Percentage of queries addressed | n/a | 100% of audit queries raised by the Auditor-General addressed by 30/06/2024 | 95% of of audit queries raised by the Auditor-General addressed by 30/06/2024 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2025 | N/A | N/A | 50% of audit queries raised by the Auditor-General addressed by 31/12/2024 | 75% of audit queries raised by the Auditor-General addressed by 31/03/2025 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2025 | 74% of audit queries raised by the Auditor-General addressed by 31/12/2024 | Achieved | N/A | N/A | All Departments | OPEX | Audit action plan and dashboard report
KPA 6: CROSS CUTTING ISSUES
CCI01 | Efficient & Credible Stratgic & Spatial Municipal Planning | Revision of a Credible Intergrated Development Plan | 81 | Date of review and adoption of credible integrated development planning by Council by 31/05/2025 | Date of review and adoption | n/a | Review and adoption of credible integrated development planning by Council by 31/05/2024 | Reviewed and adopted credible integrated development planning on the 28/05/20221 | Review and adoption of credible integrated development planning by Council by 31/05/2025 | N/A | N/A | N/A | N/A | Review and adoption of credible integrated development planning by Council by 31/05/2025 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution and Integrated development plan
CCI02 | To ensure the implementation of Spatial Development Framework | Improved Spatial Development Framework | 82 | Date of review and adoption of district Spatial Development framework by Council by 30/06/2025 | Date of review and adoption | n/a | Review and adoption of district Spatial Development framework by Council by 30/06/2024 | Reviewed and adopted district Spatial Development framework by Council on the 28/05/2024 | Review and adoption of district Spatial Development framework by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Review and adoption of district Spatial Development framework by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Community Services | OPEX | Council resolution and Spatial Development framework
CCI03 | To ensure sustainable protection and development of the environment | Development and implementation of environmental management Plan | 83 | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2025 | Date of review and adoption | All | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2024 | Reviewed and Adopted Environmental Management Plan by Council by 28/05/2024 | Review and adoption of Environmental Management Plan provided by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Review and adoption of Environmental Management Plan provided by Council by 30/06/2025 | N/A | N/A | N/A | N/A | Community Services | OPEX | Council Resolution and Environmental Management Plan
CCI04 | To create a safety and responsive environment to the community | Attending and responding to disasters and incidents with a district | 84 | Date of Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2025 | Date of submission | n/a | New Indicator | New Indicator | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2025 | N/A | N/A | N/A | N/A | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2025 | N/A | N/A | N/A | N/A | Community Services | OPEX | Disaster Management Annual Report,Council Resolution
CCI05 |  |  | 85 | Number Of Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2025 | Number of Awareness Campaigns | District -wide | New Indicator | New Indicator | Four (4)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2025 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/09/2024 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/09/2024 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2024 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/03/2025 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2025 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2024 | Achieved | N/A | N/A | Community Services | OPEX | Dated Report
CCI06 | To ensure proper communication with the public | Monitor the functioning and eficient of the Municipal Call Centre | 86 | Date of Review of the Call Centre Charter submitted to Council by 30/06/2025 | Date of review and adoption | n/a | New Indicator | New Indicator | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2025 | N/A | N/A | N/A | N/A | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2025 | N/A | N/A | N/A | N/A | Community Services | OPEX | Call Centre Charter,Council Resolution