## 23_24 APR
NAME OF MUNICIPALITY: UTHUKELA DISTRICT MUNICIPALITY - 2023_2024 ANNUAL PERFORMANCE REPORT
IDP / SDBIP NO. | Objective | Strategy | Indicator No. | Key Performance Indicator | Revised Key Performance Indicator | KPI Measurement | Ward No. | COMPARISON WITH PREVIOUS YEAR (2022/2023) |  | 2023/2024 CURRENT FINANCIAL YEAR PERFORMANCE | [6 empty] | FINANCIAL YEAR ENDED: 30 JUNE 2023
[17 empty] | 2023/2024 Budget | (2023/2024) Adjusted Budget | 2023/2024 Budget Spent | Portfolio of Evidence
[8 empty] | 2022/2023 Annual Target | 2022/2023 Annual Actual | Annual Target | Revised Annual Target | Annual Actual | STATUS Achieved | Reason for Variance | Corrective Measure | Responsible Department
STATUS Not Achieved
KPA 1: MUNICIPAL TRANFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID01 | To ensure a functional Performance Management System | Implementation of PMS Policy & Framework | 1 | Date of adoption Performance Management System by Council by 30/06/2024 | N/A | Date of adoption | N/A | Adoption of Performance Management System by Council by 30/05/2023 | Adoption of Performance Management System by Council by 30/05/2023 | Adoption of Performance Management System by Council by 30/06/2024 | N/A | Performance Management System was reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Office of the MM | OPEX | N/A | OPEX | Council resolution, PMS Policy, Framework and Standard Operating Procedures
MTID02 |  |  | 2 | Number of quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | N/A | Number of reports | N/A | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2023 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2023 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | N/A | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | Achieved | N/A | N/A | All Departments | OPEX | N/A | OPEX | Signed copies of reports & Acknowledgement letters
MTID03 |  |  | 3 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2024 | N/A | Date of submission | N/A | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2023 | Mid-Year Performance Report to the Mayor and Treasuries on the 24/01/2023 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2024 | N/A | Mid-Year Performance Report to the Mayor on the 24/01/2024 and Treasuries by 25/01/2024 | Achieved | N/A | N/A | Office of the MM | OPEX | N/A | OPEX | Proof of submission and Mid-Year Performance Report
MTID04 |  |  | 4 | Date of submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2023 | N/A | Date of submission | N/A | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2022 | Unaudited Annual Performance Report submitted to the Auditor-General on the 31/10/2022 | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2023 | N/A | Unaudited Annual Performance Report was submitted to the Auditor-General on the 31/08/2023 | Achieved | N/A | N/A | Office of the MM | OPEX | N/A | OPEX | Proof of submission and copy of the Annual Performance Report
MTID05 |  |  | 5 | Date of tabling of Annual Report to Council by 31/03/2024 | N/A | Date of tabling | N/A | Adoption of Annual Report by Council by 31/03/2023 | Annual Report adopted by Council on 30/04/2023 | Tabling of Annual Report to Council by 31/03/2024 | N/A | Annual Report was tabled to Council on the 25/01/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Office of the MM | OPEX | N/A | OPEX | Council resolution
MTID06 |  |  | 6 | Number of formal section 54/56 managers performance reviews conducted by Performance Review Panels by 30/06/2024 | N/A | Number of formal reviews | N/A | Two (2) formal section 54/56 managers' performance reviews conducted by 30/06/2023 | Two (2) formal section 45/56 managers' performance reviews conducted by 30/06/2023 | Two (2) formal section 54/56 managers' performance reviews conducted by Performance Review Panels by 30/06/2024 | N/A | Zero (0) formal section 54/56 managers' performance reviews conducted by Performance Review Panels by 30/06/2024 | Not Achieved | Formal section 54/56 managers' performance reviews have been scheduled and could not sit due to unavailability of panel members. | The Performance Reviews have been scheduled for the 27 August 2024. | Office of the MM | OPEX | N/A | OPEX | Signed Assessment Reports
MTID07 | To ensure functional risk and compliance management | Review and adopt risk and compliance governance policies | 7 | Number of risk and Compliance governance Policies adopted by Council by 30/06/2024 | N/A | Date of review | N/A | Review and adoption of risk management framework by Council by 30/06/2023 | Risk management framework reviewed and adopted by Council on the 26/06/2023 | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2024 | N/A | Seven (7) risk and Compliance governance Policies adopted by Council on the 21 May 2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Office of the MM | OPEX | N/A | OPEX | Council resolution and Policies
MTID08 |  | Ensure functionality of Risk Management Committee | 8 | Number of Risk Committee meetings held by 30 June 2024 | N/A | Number meetings | N/A | New Indicator | New Indicator | Four (4) Risk Committee meetings held by 30 June 2024 | N/A | One (1) Risk Committee meetings held on the 17/10/2024 | Not Achieved | 1)The Risk Committee Chairperson non-availability 2)The Risk Committee Chairperson non-response to reports presented by risk management unit | 1)The Municipal Manager has written to the Risk Committee Chairperson for a response non-attendance to risk committee meetings and non-submission of report to Audit & Performance Committee. 2)The Risk Officer has submitted to Senior Manco on 15 July 2024 for the termination of the Risk Committee Chairperson. The Item will be submitted to EXCO taking place on 25 July 2024. 3)An advert was developed to advertise for a Risk Committee Chairperson. | Office of the MM | OPEX | N/A | OPEX | Notice, Agenda, Attendance Register, Minutes
MTID09 | To Improve organisational Capacity | Review of organisational structure | 9 | Date of organizational structure reviewed and adopted by Council by 31/05/2024 | N/A | Date of review and adoption | N/A | Review and adoption of organizational structure by Council by 30/06/2023 | Organizational structure reviewed and adopted by Council by 28/05/2023 | Review and adoption of organizational structure by Council by 31/05/2024 | N/A | The organizational structure was reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Corporate Services | OPEX | N/A | OPEX | Council Resolution
MTID10 |  | Ensure implementation of Employment equity plan | 10 | Number of people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2024 | N/A | Number of people | N/A | 2 people from employment equity target groups employed in the three (3)highest levels of management in compliance with approved equity plan by 30/06/2023 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2023 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2024 | N/A | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2024 | Achieved | N/A | N/A | Corporate Services | OPEX | N/A | OPEX | Employment Equity Plan and appointment letters
MTID11 |  | Implementation of Workplace Skills Plan | 11 | Percentage of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | N/A | Percentage of budget spent | N/A | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2023 | Fifty Five (55%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2023 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | N/A | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | Achieved | N/A | N/A | Corporate Services | OPEX | N/A | OPEX | Financial System Print Out
MTID12 |  |  | 12 | Number of training reports submitted to Council by 30/06/2024 | N/A | Number of training reports | N/A | 4 Training reports submitted to Council by 30/06/2023 | 4 Training reports submitted to Council by 30/06/2023 | 4 Training reports submitted to Council by 30/06/2024 | N/A | 4 Training reports submitted to Council by 30/06/2024 | Achieved | N/A | N/A | Corporate Services | OPEX | N/A | OPEX | Signed Reports to Council
MTID13 | To ensure an effective and efficient HR systems that addresses Human resources within the municipality | Review and adoption of HR related policies | 13 | Date to review and adopt HR related policies by Council by 30/06/2024 | N/A | Date of review and adoption | N/A | Review and adoption of HR related policies by Council by 30/06/2023 | HR related policies reviewed and adopted by Council on the 28/05/2023 | Review and adopt HR related policies by Council by 30/06/2024 | N/A | HR related policies reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Corporate Services | OPEX | N/A | OPEX | HR related policies & Council Resolution
MTID14 | To improve Information and Communication Technology through implementation of ICT policies | Development and review of ICT policies | 14 | Number of ICT Policies developed and reviewed by the Council by the 30th June 2024 | N/A | Number of Policies | N/A | New Indicator | New Indicator | Ten (10) ICT Policy reviewed by Council by 30/06/2024 | N/A | Ten (10) ICT Policy reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Corporate Services | OPEX | N/A | OPEX | Council Resolution,ICT Policies
MTID15 | Ensure an effective and functional Fleet Services | Conducting Comprehensive reporting of Fleet Management Services | 15 | Number of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | N/A | Number of reports | N/A | New Indicator | New Indicator | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | N/A | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | Achieved | N/A | N/A | Corporate Services | OPEX | N/A | OPEX | Signed Reports
MTID16 | To ensure effective and efficient internal and external communication strategy. | Review and implementation of adopted Communication Strategy | 16 | Date of review and adoption of communication strategy by Council by 30/06/2024 | N/A | Date of review and adoption | N/A | Review and adoption of communication strategy by Council by 30/06/2023 | Communication strategy was reviewed and adopted by Council on 26/06/2023 | Review and adoption of communication strategy by Council by 30/06/2024 | N/A | Communication strategy reviewed and adopted by Council on the 21 May 2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Office of the MM | OPEX | N/A | OPEX | Communication Strategy & Council Resolution
MTID17 | Improve communications with external Stakeholders | Development of Municipal Communication Strategy | 17 | Number of Municipal Newsletters published for each financial year by 30 June 2024 | N/A | Number of Newsletters | N/A | New Indicator | New Indicator | Four (4) Municipal newsletters published by 30/06/2024 | N/A | Four (4) Municipal newsletters published by 30/06/2024 | Achieved | N/A | N/A | Office of the MM |  | N/A | OPEX | Municipal newsletters, Proof of Publication
MTID18 | To report & monitor Service Delivery | Submission of quarterly reports to COGTA | 18 | Number of Circular 88 reports submitted to Provincial COGTA by 30/06/2024 | N/A | Number of reports | N/A | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2023 | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2023 | 4 Circular 88 reports submitted to Provincial COGTA by 30/06/2024 | N/A | 2 Circular 88 reports submitted to Provincial COGTA by 30/06/2024 | Not Achieved | Information relating to Financial Viability has delayed completion of the Quarter 3 and Quarter 4 Report . | Circular 88 reports relating to Quarter 3 and Quarter 4 will be forwarded to COGTA by the 31 August 2024. | Office of the MM | OPEX | N/A | OPEX | Circular 88 reports , Proof of submission
MTID19 | To improve the municipal Audit opinion | Effective Audit and Performance Committee | 19 | Number of Audit and Performance Committee meetings held by 30/06/2024 | N/A | Number of meetings | N/A | 4 Audit and Performance Committee meetings held by 30/06/2023 | 4 Audit and Performance Committee meetings held by 30/06/2023 | 4 Audit and Performance Committee meetings held by 30/06/2024 | N/A | 8 Audit and Performance Committee meetings held on the 7/07/2023,25/08/2023,29/09/2023,19/10/2023,13/12/2023,14/02/2024,16/05/2024,20/05/2024 | Achieved | The APAC on the month of August 2023 sat twice to review Financial, on the month of May 2024 the committee sat twice to review the 2024/2025 Budget. | N/A | Office of the MM | OPEX | N/A | OPEX | Minutes with attendance registers
MTID20 |  | Oversight meetings held | 20 | Number of MPAC meetings convened by 30/06/2024 | N/A | Number of meetings | N/A | 4 MPAC meetings convened by 30/06/2023 | 4 MPAC meetings convened by 30/06/2023 | 4 MPAC meetings convened by 30/06/2024 | N/A | 5 MPAC meetings convened on the 31/10/2023,07/11/2023,10/02/2024,15/03/2024,05/06/2024 | Achieved | The MPAC sat in the month of October and November for prior 2022/2023 UIFW Investigations. | N/A | Office of the MM | OPEX | N/A | OPEX | Minutes with attendance registers
KPA 2: BASIC SERVICE DELIVERY
BSD01 |  | Provide community water supply | 21 | Number of Households provided with water to eradicate backlock by 30/06/2024 | N/A | Number | Various | 1743 of Households provided with water to eradicate backlock by 30/06/2023 | 1743 of Households provided with water to eradicate backlock by 30/06/2023 | 750 of Households provided with water to eradicate backlock by 30/06/2024 | Four Hundred and Sixty two (462) provided with water to eradicate backlock (Okhahlamba East and West)(Loskop) by 30/06/2024 | 441 Households provided with water to eradicate backlock by 30/06/2024 | Not Achieved | Loskop Project: Original Scope of works indicated 95 on planning stage, upon construction 2 new households were included, hence achievement for Loskop project was 97. On Implementation of Okhahlamba East and West the original scope the number was estimated. On Implementation of the project it was therefore discovered that the registered household were found to be not compliant to the Framework of 1 tap per household. | The Service provider reported that the project has been completed and the practical completion certificate was handed to the Municipality. | Water, Sanitation & Technical Services | R30 000 000,00 R21 642 942,86 | R16 000 000,00 R45 843 188,93 | R15 500 937.65 R51 352 673,66 | Signed Engineers Report, Beneficiary listing and Happy letters
BSD02 |  |  | 22 | Number of Water treatment plant constructed at Bergvile WTW to be completed by 30/06/2024 | Number of sedimentation tank constructed at Bergvile WTW to be completed by 30/06/2024 | Number | 11 | New Indicator | New Indicator | (1) of sedimentation tank constructed at Bergvile WTW to be completed by 30/06/2024 | N/A | One (1) sedimentation tank constructed at Bergvile WTW completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R17 000 000,00 | R28 275 455,15 | R36 440 830,34 | Signed Engineers Report
BSD03 |  |  | 23 | Number of KM's of bulk rising main pipeline constructed at Bergville WTW by 30/06/2024 | N/A | Number | 11 | New Indicator | New Indicator | 1.2 kilometres of bulk rising main pipeline constructed at Bergville WTW by 30/06/2024 | N/A | 1.2 kilometres of bulk rising main pipeline constructed at Bergville WTW completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD03.1 |  |  | 24 | Number of Pump station Completed at Bergvile WTW to be completed by 30/06/2024 | N/A | Number of Pump |  | New Indicator | New Indicator | N/A | One (1) of Pump station Completed at Bergvile WTW to be completed by 30/06/2024 | Two (2) Pump stations at Bergvile WTW completed by 30/06/2024 | Achieved | As part of elevating the community, the main contractor appointed 4 local Contract Participating Goals (CPG’s) which were allocated portion of the works. Additionally other specialist were appointed for other specialised sections of the works. These appointments elevated the progress on site and the contractor achieved more than the planned targets. | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD04 |  |  | 25 | Date of Appointment of Contractor at Colenso and Rosboom Bulk Water: Phase 2 to be completed by 30/06/2024 | N/A | Date of appointment | 25 | New Indicator | New Indicator | Appointment of Contractor at Colenso and Rosboom Bulk Water: Phase 2 to be completed by 30/06/2024 | N/A | No Appointment of Contractor for Colenso and Rosboom Bulk Water: Phase 2 by 30/06/2024 | Not Achieved | The Business Plan approval was delayed due to EIA and WULA application was pending approval. (EIA) was approved in August 2023 a WULA was approved February 2024. | The Business Plan approval is currently on hold as the Municipality's implementation plan is currently overcommitted. | Water, Sanitation & Technical Services | 0 | 0 | 0 | Signed Engineers Report
BSD05 |  |  | 26 | Number of bulk pipeline (Rising main from Rose Hill Reservoir to high Tower) constructed at Ezakheni WCDM: Phase 2 by 30/06/2024 | N/A | Number of kilometres | 1,2,3,4,5,8,13 & 20 | New Indicator | New Indicator | 1,03 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 30/06/2024 | 0,28 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 30/06/2024 | 0 km of bulk pipeline (Rising main from Rose Hill Reservoir to high Tower) was constructed at Ezakheni WCDM Phase 2 by 30/06/2024 | Not Achieved | Service Provider reported delayed appointments of local labours and CLO. Subsequently, Local business forums hindering the project progress by demanding to supply bedding material locally. | ISD intervened and resolved the issue of employment of labourers and business forums demands. The completion of the chambers are projected to be completed in 2024/2025 financial year | Water, Sanitation & Technical Services | R 15 000 000,00 | R15 000 000,00 | R8 507 871,92 | Signed Engineers Report
BSD06 |  |  | 27 | Number of Bulk meter chambers to be installed at Ezakheni WCDM: Phase 2 by 30/06/2024 | N/A | Number | 1,2,3,4,5,8,13 & 20 | New Indicator | New Indicator | 12 Bulk meter chambers to be installed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 07 Bulk meters changes to be installed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 0 Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) was installed at Ezakheni WCDM: Phase 2 by 30/06/2024 | Not Achieved | Service Provider reported delayed appointments of local labours and CLO. Subsequently, Local business forums hindering the project progress by demanding to supply bedding material locally. | ISD intervened and resolved the issue of employment of labourers and business forums demands. The completion of the chambers are projected to be completed in 2024/2025 financial year | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD06,1 |  |  | 28 | Kilometres of reticulation (C section subzone-ac pipe replacement) pipeline constructed at Ezakheni WCDM: Phase 2 by 30/06/2024 | N/A | Kilometres | 1,2,3,4,5,8,13 & 20 | New Indicator | New Indicator | N/A | 0,225 reticulation pipeline constructed at Ezakheni WCDM: Phase 2 by 30/06/2024 | 3,211 kM's of reticulation pipeline constructed at Ezakheni WCDM: Phase 2 completed by 30/06/2024 | Achieved | There was a change method, Horizontal directional drilling was implemented which was suitable underground laying of HDPE at no additional cost | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD07 |  |  | 29 | Date of Completion of Designs at KwaMkhize Bulk Water Supply and Reticulation Network by 30/06/2024 | N/A | Date of completion | 11 & 12 | New Indicator | New Indicator | Completion of Designs at KwaMkhize Bulk Water Supply and Reticulation Network by 30/06/2024 | This indicator is no longer applicable for the 23/24 financial year. | This indicator is no longer applicable for the 23/24 financial year. | N/A | This indicator was erroneously included in the 23/24 SDBIP and was considered no longer applicable during the mid-year adjustments as the designs were completed in February 2022. | N/A | Water, Sanitation & Technical Services | R944,597.31 | 0 | 0 | Signed Engineers Report
BSD08 |  |  | 30 | Date of Site Completion of site establishment at Langkloof and Bulk Supply: Phase 1 by 30/09/2023 | N/A | Date of completion | 10 | New Indicator | New Indicator | Completion of site establishment at Langkloof and Bulk Supply: Phase 1 by 30/09/2023 | N/A | Site establishment at Langkloof and Bulk Supply: Phase 1 completed by 31/12/2023 | Achieved | SCM processes were completed in Quarter 2. Site Establishment was therefore completed in Quarter 2 on Commencement of the project | N/A | Water, Sanitation & Technical Services | R5 000 000,00 | R16 759 299,75 | R14 094 876,42 | Signed Engineers Report
BSD09 |  |  | 31 | Number of km reticulation pipelines constructed in Langkloof Package Plant and Bulk Supply by 30/06/2024 | Number of km of bulk rising main constructed in Langkloof Package Plant and Bulk Supply by 30/06/2024 | Number of Kilometres | 10 | New Indicator | New Indicator | 7,7 km reticulation pipeline to be constructed at Langkloof Package Plant by 30/06/2024 | 1,6 km bulk rising main to be constructed at Langkloof Package Plant by 30/06/2024 | 1,6 km bulk rising main constructed at Langkloof Package Plant completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD10 |  |  | 32 | Number of Kilometres of reticulation pipelines constructed at Ennersdale/ Ephangwini(Loskop) ward 4 by 30/09/2024 | N/A | Number of Kilometres | 4 | 21,9 Kilometres of reticulation pipelines constructed at Ennersdale/Ephangwini ward 4 by 30/06/2023 | 21,9 Kilometres of reticulation pipelines constructed at Ennersdale/Ephangwini ward 4 by 30/06/2023 | 1 km of reticulation to be constructed at Ennersdale/Ephangwini ward 4 by 30/09/2023 | This indicator is no longer applicable for the 23/24 financial year. | This indicator is no longer applicable for the 23/24 financial year. | N/A | This indicator is no longer applicable for the 23/24 F/Y as the project is currently on hold due to resignation of the site agent. Furthermore, it was established that there was a breach of contract, this project is currently placed on hold and under intention to terminate. | N/A | Water, Sanitation & Technical Services | R4,000,000.00 | 0 | 0 | Signed Engineers Report
BSD11 |  |  | 33 | Date of Completion of winterton sanitation designs by 30/06/2024 | N/A | Date of completion | 1 | New Indicator | New Indicator | Completion of sanitation designs at Winterton by 30/06/2024 | N/A | Sanitation designs at Winterton was not completed by 30/06/2024 | Not Achieved | A comprehensive funding application, accompanied by a technical report, was submitted to the Department of Cooperative Governance and Traditional Affairs (CoGTA) and the Department of Water and Sanitation (DWS). The aim was to secure funding for Inception and 50% of the Concept & Viability phase for this project. The application was successful. The Inception and a draft Concept & Viability was completed and the respective reports were submitted. No Design phase was completed and therefore no Detail Design Report could be submitted. | The detailed design stage of the project cannot commence until the PDR and IRS have been approved by the DWS. | Water, Sanitation & Technical Services | R1 549 786,95 | R4 460 627,44 | R4 460 627,44 | Signed Engineers Report
BSD12 |  |  | 34 | Completion of winterton water supply designs by 30/06/2024 | N/A | Date of completion | 1 | New Indicator | New Indicator | Completion of winterton water supply designs by 30/06/2024 | N/A | Water supply design at Winterton was not completed by 30/06/2024 | Not Achieved | A comprehensive funding application, accompanied by a technical report, was submitted to the Department of Cooperative Governance and Traditional Affairs (CoGTA) and the Department of Water and Sanitation (DWS). The aim was to secure funding for the Inception, Concept & Viability, and 40% of the Design phase for this project. The application was successful. The Inception and Concept & Viability was completed and the respective reports were submitted. Only 40% of the Design phase was completed and therefore no Detail Design Report could be submitted. | The detailed design stage of the project cannot commence until the PDR and IRS have been approved by the DWS. | Water, Sanitation & Technical Services | R1 377 220,45 | R2 598 649,25 | R 2 598 649,25 | Signed Engineers Report
BSD13 |  |  | 35 | Number district wide springs protected by 30/06/2024 | N/A | Number | Various | Twelve (12) district wide springs protected by 30/06/2024 | Twelve (12) district wide springs protected by 30/06/2024 | Twelve (12) spring protected district wide by 30/06/2024 | Seven (07) spring protected district wide by 30/06/2024 | Six (6) spring protected district wide completed by 30/06/2024 | Not Achieved | On implementation of project, it was discovered that one springs went dry; therefore, couldn't completed commissioning of the spring since there was no water supply. | This project was completed in December 2023 with only 6 springs reported as protected district wide. Completed certificate was issued to the Municipality. | Water, Sanitation & Technical Services | R 27 000 000,00 | R27 768 210,28 | R27 768 210,28 | Signed Engineers Report
BSD14 |  |  | 36 | Number of drilled and equipped boreholes district wide by 30/06/2024 | N/A | Number | Various | Ten (10) boreholes drilled and equipped | Ten (10) boreholes drilled and equipped | Ten (10) boreholes drilled and equipped by 30/06/2024 | Seven (7) boreholes drilled and equipped by 30/06/2024 | Twelve (12) boreholes drilled and equipped completed by 30/06/2024 | Achieved | The Outstanding boreholes wich were not commisioned in the prior year were included in the scope. | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD15 | To provide sanitation system to the community | Provision and maintenance of sanitation infrastructure | 37 | Number of kilometres of Reticulation(HDPE Pipeline and PVC Pipeline) constructed at Fitty Park Community water project: Phase 2 by 30/06/2024 | N/A | Number of Kilometres | 7 & 28 | New Indicator | New Indicator | 13 Kilometres of reticulation (HDPE Pipeline and PVC Pipeline) pipelines constructed at Fitty Park Community Water Project by 30/06/2024 | 13,7 Kilometres of reticulation (HDPE Pipeline and PVC Pipeline) pipelines constructed at Fitty Park Community Water Project by 30/06/2024 | 13,7km reticulation (HDPE Pipeline and PVC Pipeline) pipeline constructed at Fitty Park Community Water Project completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R7 000 000,00 | R9 170 830,45 | R3 802 136,63 | Signed Engineers Report
BSD16 |  |  | 38 | Number of VIP toilets constructed by 30/06/2024 | N/A | Number | Various | 3000 VIP toilets constructed by 30/06/2023 | 3000 VIP toilets constructed by 30/06/2023 | 2000 VIP toilets constructed by 30/06/2024 | N/A | 2000 VIP toilets was constructed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R18 000 000,00 | R23 000 000,00 | R26 387 891,98 | Signed Engineers Report, Beneficiary listing and Happy letters
BSD17 | To provide infrastructure and sustainable basic services | Provide community water supply | 39 | Date of completion of designs of Fitty Park Umhlumayo Bulk water supply infrastructure upgrade Tugela Estate by 30/06/2024 | N/A | Date of completion | 7, 28, 29 & 30 | New Indicator | New Indicator | Date of completion of designs of Fitty Park Umhlumayo Bulk water supply infrastructure upgrade Tugela Estate by 30/06/2024 | N/A | Designs of Fitty Park Umhlumayo Bulk water supply infrastructure upgrade Tugela Estate was not been completed by 30/06/2024 | Not Achieved | Preliminary Designs have been completed and submitted to Municipality. There are delays in the completion of Designs | The Service Provider to present the Draft PDR and the IRS to the uThukela District Municipality. The Service Provider to obtain outstanding information and comments on the PDR and IRS from the uThukela District Municipality. The Service Provider to complete the preliminary designs and drawings based on comments received. The Service Provider DHV to complete the PDR and IRS based on the completed preliminary designs and drawings. The Service Provider DHV to submit the application for funding based on the approved PDR and IRS. Environmental Assessment Practitioner (EAP) to submit the Basic Assessment for Environmental Authorization. EAP to submit applications for various Water Use Licenses. Commence land acquisition process for the various infrastructure, Royal HaskoningDHV and uThukela District Municipality to work together on this activity. Royal HaskoningDHV to submit the Eskom power supply applications for the relevant infrastructure. | Water, Sanitation & Technical Services | R8 391 834,32 | R10 380 123,27 | R9 906 956.08 | Signed Engineers Report
BSD18 |  |  | 40 | Number of Kilometres of reticulation pipelines constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2024 | N/A | Number of kilometres | 14 | 12 Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2023 |  | 0,51 kilometres of reticulation pipeline to constructed Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2024 | N/A | 0,51 kilometres of reticulation pipeline constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R21 642 942,86 | R45 843 188,93 | R51 352 673,66 | Signed Engineers Report
BSD19 |  |  | 41 | Number of Kilometres of bulk pipelines constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 31/12/2023 | N/A | Number of kilometres | 14 | 0,2 Kilometres of Bulk pipelines Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2023 | 0,2 Kilometres of Bulk pipelines Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2023 | 0,6 of kilometres of bulk pipeline to constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 31/12/2023 | N/A | 0,6 of kilometres of bulk pipeline constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 completed by 31/12/2023 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD20 |  |  | 42 | Number of Reservoirs constructed at Okhahlamba Ward 14 East by 31/03/2024 | N/A | Number | 14 | New Indicator | New Indicator | (1) One Reservoir constructed at Okhahlamba Ward 14 East by 31/03/2024 | N/A | One (1) Reservoir constructed at Okhahlamba Ward 14 East completed by 31/03/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD21 |  |  | 43 | Number of Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/06/2024 | N/A | Number of Kilometres | 14 | 12 Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 02 by 30/06/2023 | 12 Kilometres of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 02 by 30/06/2023 | 0,275 kilometres of reticulation pipeline to constructed by 30/06/2024 | N/A | 0,275 kilometres of reticulation pipeline construction completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD22 |  |  | 44 | Number of Kilometres bulk pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/06/2024 | N/A | Number of kilometres | 14 | 0,2 Kilometres of Bulk pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 02 by 30/06/2023 | 0,2 Kilometres of Bulk pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 02 by 30/06/2023 | 0,7 of Kilometres bulk pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/06/2024 | N/A | 0,7 Kilometres of bulk pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD23 |  |  | 45 | Number of Reservoirs constructed at Okhahlamba Ward 14 West by 31/03/2024 | N/A | Number | 14 | New Indicator | New Indicator | One (1) Reservoir constructed at Okhahlamba (Vimbikhalo)Ward 14 East by 31/03/2024 | N/A | One (1) Reservoir constructed at Okhahlamba (Vimbikhalo)Ward 14 East completed by 31/03/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD24 |  |  | 46 | Number of production boreholes to be equipped at Okhahlamba by 30/06/2024 | N/A | Number | 2,3,14 | New Indicator | New Indicator | 10 production boreholes to be drilled at Okhahlamba by 31/12/2023 | Eight (8) production boreholes to be drilled at Okhahlamba by 30/06/2024 | Eight (8) production boreholes drilled at Okhahlamba completed by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD25 |  |  | 47 | Number of handpumps to be equipped at Okhahlamba by 30/06/2024 | N/A | Number | 2,3,14 | New Indicator | New Indicator | 33 handpumps to be drilled at Okhahlamba by 30/06/2024 | N/A | 10 handpumps drilled at Okhahlamba completed by 30/06/2024 | Not Achieved | Tender was opened on the 14 December 2024,SCM processes were finalised in Quarter 2 | SCM processes were finalised in Quarter 2.Contactor was therefore appointed in Quarter 2 | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD26 |  |  | 48 | Appointment of 2 Contractors at Okhahlamba (Vimbukhalo) by 31/03/2024 | N/A | Date | 14 | New Indicator | New Indicator | Appointment of 2 Contractor at Okhahlamba (Vimbukhalo) Ward (14) by 31/03/2024 | N/A | Contractors at Okhahlamba (Vimbukhalo) Ward (14) appointed on the 6 May 2024 and 02 May 2024 respectively | Achieved | This target was achieved during the 23/24 financial year; even though the target was not achieved as per targeted date of 31/03/2024. This is was due to SCM delays as the tender was opened on the 14 December 2023, SCM processes were finalised in Quarter 3. | SCM processes were finalised in Quarter 2 & 3 and the two Contractors were appointed during quarter 3 of the 23/24 financial year. | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD27 |  |  | 49 | Number of bulk pipeline (AC pipeline) constructed at Steadville WCDM by 30/06/2024 | N/A | Number of Kilometres | 9 & 10 | New Indicator | New Indicator | 7 kilometres of bulk pipeline (AC pipeline) constructed at Steadville WCDM by 30/06/2024 | 3,779 kilometres of bulk pipeline (AC pipeline) constructed at Steadville WCDM by 30/06/2024 | 1,844 kilometres of bulk pipeline (AC pipeline) constructed at Steadville WCDM completed by 30/06/2024 | Not Achieved | There was a Labour Strike which created delay on site. The Local Business forum halted progress on site. Challenges in the supply and delivering of material its at a slow pace | ISD resolved issues pertaining to labour. The Supplier of the material was thereafter changed and a new supplier was appointed | Water, Sanitation & Technical Services | R 13 800 000,00 | R 10 240 987,49 | R12 645 173,27 | Signed Engineers Report
BSD28 |  |  | 50 | Number of installation of bulk metering chambers at Steadville WCDM by 31/03/2024 | N/A | Number | 9 & 10 | New Indicator | New Indicator | (5) installation of bulk metering chambers at at Steadville WCDM by 30/06/2024 | (3) installation of bulk metering at Steadville by 31/03/2024 | None (0) installation of bulk metering at Steadville completed by 31/03/2024 | Not Achieved | There was a Labour Strike which created delay on site. The Local Business forum halted progress on site. Challenges in the supply and delivering of material its at a slow pace | ISD resolved issues pertaining to labour. The Supplier of the material was thereafter changed and a new new supplier was appointed by the contractor. | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD29 |  |  | 51 | Number of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | N/A | Number of Kilometres | 12 | New Indicator | New Indicator | 10 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | 2,45 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | 1,638 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement completed by 30/06/2024 | Not Achieved | The Local Business forum halted progress on site. Challenges in the supply and delivering of material its at a slow pace | The Supplier of the material was thereafter changed and a new supplier was appointed | Water, Sanitation & Technical Services | R 19 000 000,00 | R 11 000 000,00 | R10 965 185.20 | Signed Engineers Report
BSD30 |  |  | 52 | Number of installation of bulk metering at Ladysmith AC pipeline replacement by 31/03/2024 | N/A | Number | 12 | New Indicator | New Indicator | (5) installation of bulk metering at Ladysmith AC pipeline replacement by 31/03/2024 | (3) installation of bulk metering at Ladysmith AC pipeline replacement by 31/03/2024 | (0) installation of bulk metering at Ladysmith AC pipeline replacement by 31/03/2024 | Not Achieved | The Local Business forum halted progress on site. Challenges in the supply and delivering of material its at a slow pace | The Supplier of the material was thereafter changed and a new supplier was appointed The completion of the chambers are projected for the 2024/2025 | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD31 |  |  | 53 | Number of KM's of UPVC Mains constructed at KwaNobamba/Ezitendeni Water Supply by 30/09/2023 | N/A | Number of Kilometres | 21 | New Indicator | New Indicator | 0,3 Km's of UPVC Mains to be constructed at KwaNobamba/Ezitendeni Water Supply by 30/09/2023 | 4 Km's of UPVC Mains to be constructed at KwaNobamba/Ezitendeni Water Supply by 30/09/2023 | 4 Km's of UPVC Mains constructed at KwaNobamba/Ezitendeni Water Supply completed by 30/09/2023 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R1 277 889,01 | R988 488,22 | R988 488,22 | Signed Engineers Report
BSD31.1 | To provide infrastructure and sustainable basic services | Provide community water supply | 54 | Date of Site Establishment completed at Ezakheni E Sanitation by 31/03/2024 | N/A | Date | 6 | New Indicator | New Indicator | N/A | Date of Site Establishment completed at Ezakheni E Sanitation by 31/03/2024 | Site Establishment at Ezakheni E Sanitation completed by 31/03/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R1 681 975,85 | R1 596 591,00 | R723 022,26 | Signed Engineers Report
BSD31.2 |  |  | 55 | Number manholes constructed Ezakheni E completed by 30 June 2024 | N/A | Number | 6 | New Indicator | New Indicator | N/A | (18) manholes constructed(New 3)Refurbished(15)at Ezakheni E completed by 30 June 2024 | (15) manholes constructed (New 5) (Refurbished 10) at Ezakheni E completed by 30 June 2024 | Not Achieved | Delays in scope verification Sequence of manholes as per the issued maps was not practical as it skipped several manholes. | The challenges necessitated that consultations be done to include the various manholes and unblocking . | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD31.3 |  |  | 56 | Number of installation of 1,0 MI GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30 June 2024 | N/A | Number | 10,11 | New Indicator | New Indicator | N/A | 1,0 MI GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30 June 2024 | (0 )installation of 1,0 MI GMS Reservoir completed at Ntabamhlophe Community Water Supply Scheme Upgrade of Bosch by 30 June 2024 | Not Achieved | Delays with Contractual documents approval. Health and Safety issues encounted by the contractor | 2 Notices were issued to expedite works. Revised programme of works and works will be completed in 2024/2025 financial year | Water, Sanitation & Technical Services | R5 361 437,24 | R4 935 053.47 | R1 530 812,29 | Signed Engineers Report
BSD31.4 |  |  | 57 | Number of Sewer Pump Stations (M&E) completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 31/03/2024 | N/A | Number | 21 | New Indicator | New Indicator | N/A | Two (2) of Sewer Pump Stations (M&E) completed at KwaNobamba /Ezitendeni Sanitation WWTW completed at 31/03/2024 | Zero (0) of Sewer Pump Stations (M&E) completed at KwaNobamba /Ezitendeni Sanitation WWTW at 31/03/2024 | Not Achieved | Delay on the approval of the additional funding from the Funder. The project have interlinking phases civil works contract undertaking the construction of WWTW is not complete preventing resuming of installation for various Mechanical and Electrical elements. | Civil works and Mechanical & Electrical Contractors will resume with works simultaneously and revised completion of the mechanical and electrical works on the pump stations will be completed by December 2024 | Water, Sanitation & Technical Services | R56 000 000,00 | R15 000 000,00 | R5 270 119,56 | Signed Engineers Report
BSD31.5 |  |  | 58 | Number of Sedimentation Tank completed at Kwanobamba/Ezitendeni Sanitation project by 30 June 2024 | N/A | Number | 21 | New Indicator | New Indicator | N/A | One (1) of Sedimentation Tank (M&E) completed at Kwanobamba/Ezitendeni Sanitation project by 30 June 2024 | Zero (0) of Sedimentation Tank (M&E) completed at Kwanobamba/Ezitendeni Sanitation project by 30 June 2024 | Not Achieved | Delay on the approval of the additional funding from the Funder. The project have interlinking phases civil works contract undertaking the construction of WWTW is not complete preventing resuming of installation for various Mechanical and Electrical elements. | Civil works and Mechanical & Electrical Contractors will resume with works simultaneously and revised completion of the mechanical and electrical works on the pump stations will be completed by December 2024 | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD31.6 |  | Provision and maintenance of sanitation infrastructure | 59 | Date of Site Establishment at Loskop Abstraction WTW by 31/03/2024 | N/A | Date | 5 | New Indicator | New Indicator | N/A | Date of Site Establishment at Loskop Abstraction WTW by 31/03/2024 | Site Establishment at Loskop Abstraction WTW completed by 31/03/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | R30 000 000,00 | R16 000 000,00 | R15 500 937.65 | Signed Engineers Report
BSD31.7 |  |  | 60 | Number of bulk pipeline at Loskop Abstraction WTW by 30/06/2024 | N/A | Number | 5 | New Indicator | New Indicator | N/A | 0,14 Kilometres of bulk pipeline at Loskop Abstraction WTW by 30/06/2024 | 0,11 Kilometres of bulk pipeline at Loskop Abstraction WTW completed by 30/06/2024 | Not Achieved | The contractor had challenges in removing the hard rock, cash flow changelles from the contactor | The outstanding kilometres will be completed in 2024/2025 financial year | Water, Sanitation & Technical Services |  |  |  | Signed Engineers Report
BSD32 | To ensure safe and healthy potable water | Implement an effective water and waste water monitoring program | 61 | Number of water treatment plants monitored by 30/06/2024 | N/A | Number | N/A | 15 water treatment plants monitored by 30/06/2023 | 15 water treatment plants monitored by 30/06/2023 | 15 water treatment plants monitored by 30/06/2024 | N/A | 15 water treatment plants were monitored by 30/06/2024 | Achieved | N/A | N/A | Community Services | OPEX | OPEX | OPEX | Signed reports
BSD33 |  |  | 62 | Number of waste water treatment works monitored by 30/06/2024 | N/A | Number | N/A | 9 waste water treatment works monitored by 30/06/2023 | 9 waste water treatment works monitored by 30/06/2023 | 9 waste water treatment works monitored by 30/06/2024 | N/A | 9 waste water treatment works were monitored by 30/06/2024 | Achieved | N/A | N/A | Community Services | OPEX | OPEX | OPEX | Signed reports
BSD34 | To enhance consumer protection with sufficient food control | Monitor compliance of food selling outlets | 63 | Number of food handling premises inspected by 30/06/2024 | N/A | Number | N/A | 864 food handling premises inspected by 30/06/2023 | 864 food handling premises inspected by 30/06/2023 | 864 food handling premises inspected by 30/06/2024 | 1118 food handling premises inspected by 30/06/2024 | 1373 food handling premises were inspected by 30/06/2024 | Achieved | Staff were no longer sharing vehicles , inspections were done independently hence the increase in the number of premises inspected. There were also new emerged businesses ( new applications) Re inspection- to ensure compliance also contributed | N/A | Community Services | OPEX | OPEX | OPEX | Signed reports
KPA 3: LOCAL ECONOMIC DEVELOPMENT
LED01 | To Increase Job opportunities | Implement Expanded Public Works Programme (EPWP) | 64 | Number of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | N/A | Number of EPWP jobs | District -wide | 1019 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2023 | 849 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2023 | 1032 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | N/A | 799 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | Not Achieved | Delay in the commencement of projects, hence delays in employment of EPWP. | UTDM has implemented the projects which will assist in reaching target for 2024/2025 FY | Water, Sanitation & Technical Services | R1,816,000.00 | N/A | R1,816,000.00 | Signed reports
LED02 |  |  | 65 | Number of EPWP reports submitted to the funder by 30/06/2024 | N/A | Number of EPWP reports | District -wide | 12 EPWP reports submitted to the funder by 30/06/2023 | 12 EPWP reports submitted to the funder by 30/06/2023 | 12 EPWP reports submitted to the funder by 30/06/2024 | N/A | 12 EPWP reports were submitted to the funder by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  |  | Signed reports
LED02.1 |  |  | 66 | Number of FTE's created through LED initiatives, including capital projects, by 30/06/2024 | N/A | Number of FTE's | District -wide | New Indicator | New Indicator | N/A | Three hundred and forty four (344) of FTE's created through LED initiatives, including capital projects, by 30/06/2024 | One Hundred and eighty one (181) FTE's created through LED initiatives, including capital projects by 30/06/2024 | Not Achieved | Duration of projects affecting the number of days worked | UTDM to consider implementing projects for 12 months duration | Water, Sanitation & Technical Services |  | OPEX |  | Attendance Registers,
LED03 | To enhance the Uthukela Local Economic Development | LED policy reviewed | 68 | Date of review and adoption of LED strategy by Council 30/06/2024 | N/A | Date of review | District -wide | Review and adoption of LED strategy by Council by 30/06/2023 | LED strategy by Council by 28/05/2023 | Review and adoption of LED strategy by Council by 30/06/2024 | N/A | LED strategy not reviewed and adopted by Council by 30/06/2024 | Not Achieved | Each year for the last 10 years or more we have received no funding for project implementation, which puts in doubt the need to review the LED Strategy The Agency Agreement, states that they are contracted for the implementation of the LED Strategy (As the only recipients of LED Funding from uThukela DM) The District has received no funding, we do not have the funds to employ specialist services, such as Economists to inform an LED Review. | The District will review and assess the relevance of Projects and Programmes internally and adjust the LED strategy accordingly in the 2024/2025 financial year. | Social and Economic Services | OPEX | OPEX | OPEX | Council Resolution and LED strategy
LED04 |  | Convene district LED/Tourism Forum meetings | 69 | Number of district LED/Tourism forums meetings held by 30/06/2024 | N/A | Number of meetings | N/A | New Indicator | New Indicator | 4 district LED/Tourism forums meetings held by 30/06/2024 |  | 4 district LED/Tourism forums meetings were held by 30/06/2024 | Achieved | N/A | N/A | Social and Economic Services | OPEX | OPEX | OPEX | Signed reports
KPA 4: GOOD GOVERNANCE & PUBLIC PARTICIPATION
GGPP01 | To ensure good and effective governance | Participate the IGR Structures | 70 | Percentage of functional IGR Structures by 30/06/2024 | N/A | Percentage of functional structures | N/A | 100% of functional IGR Structures by 30/06/2023 | 100% of functional IGR Structures by 30/06/2023 | 100% of functional IGR Structures by 30/06/2024 | N/A | 17% of functional IGR Structures by 30/06/2024 | Not Achieved | Clusters were not convened due to non-availability of Political Principals. Only one Cluster was functional. | The Non Functionality of IGR Structures have been reported to KZN COGTA. For the 2024/2025 Financial year proposed dates have forwarded to all Municipalities and the functionality of the structures will be monitored on a Quarterly basis | Office of the MM | OPEX | OPEX | OPEX | Notice, minutes & attendance registers
GGPP02 | To promote the interest of designated groups | Participate in the annual programmes | 71 | Number of Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | N/A | Number of special programmes | All | 7 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2023 | 8 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2023 | 7 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | N/A | 0 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | Not Achieved | The Special Programmes was not allocated with budget for the 2023/2024 financial year | This Target will be removed on the 2024/2025 Financial as the Municipality is currently under financial constraints | Office of the MM | OPEX | OPEX | OPEX | Signed Reports
KPA 5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM01 | To ensure legally sound financial viability and management | Timeous financial reporting and management | 72 | Percentage of MIG Expenditure by 30/06/2024 | N/A | Percentage of expenditure | N/A | 100% of MIG expenditure by 30/06/2023 | 100% of MIG expenditure by 30/06/2023 | 100% of MIG expenditure by 30/06/2024 | N/A | 100% of MIG expenditure by 30/06/2024 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | MIG | R221342000 | 221342000 | Grant expenditure report and proof of payments
MFVM02 |  |  | 73 | Percentage of annual allocation to free basic services spent by 30/06/2024 | N/A | Percentage spent | N/A | 100% of annual allocation to free basic services spent by 30/06/2023 | 0% of annual allocation to free basic services spent by 30/06/2023 | 100% of annual allocation to free basic services spent by 30/06/2024 | N/A | 9.5% of annual allocation to free basic services spent by 30/06/2024 | Not Achieved | Low Collection Rate | Implementation of the Revenue Enhancement Strategy | Budget & Treasury Office | OPEX | R35000000 | R6,189,300 Indigent rebate. R1,911,693 water tankering | Signed reports
MFVM03 |  |  | 74 | Percentage of operating budget spent by 30/06/2024 | N/A | Percentage spent | N/A | 100% of operating budget spent by 30/06/2023 | 74% of operating budget spent by 30/06/2023 | 100% of operating budget spent by 30/06/2024 | N/A | 94.5% of operating budget spent by 30/06/2024 | Not Achieved | Unfunded Budget | Implementation of the Budget Funding Plan Strategies | Budget & Treasury Office | OPEX | R936405000 | R1,190,853,532 | Signed reports
MFVM04 |  |  | 75 | Percentage of capital budget spent by 30/06/2024 | N/A | Percentage spent | N/A | 100% of capital budget spent by 30/06/2023 | 100% of capital budget spent by 30/06/2023 | 100% of capital budget spent by 30/06/2024 | N/A | 100% of capital budget spent by 30/06/2024 | Achieved | N/A | N/A | Budget & Treasury Office | CAPEX | R306869000 | R234,210,902 | Signed reports
MFVM05 |  |  | 76 | Percentage of repairs and maintenance spent by 30/06/2024 | N/A | Percentage spent | N/A | 100% of repairs and maintenance spent by 30/06/2023 | 38% of repairs and maintenance spent by 30/06/2011 | 100% of repairs and maintenance spent by 30/06/2024 | N/A | 126% of repairs and maintenance spent by 30/06/2024 | Achieved | The overspending was a result of old infrasture which required to be replaced for the supply of water. | N/A | Budget & Treasury Office | OPEX | R77707935 | R109,512,064 | Signed reports
MFVM06 |  |  | 77 | Ratio on financial viability in terms of debt coverage by 30/06/2024 | N/A | Ratio | N/A | 1:03 | 8,49: 03 | 1:03 | N/A | 01:006 | Not Achieved | Low Collection Rate- Current Economic Conditions is compromise the livehood of municipal customers for failure to honor the accounts when they become due. | Implementation of the Revenue Enhancement Strategy | Budget & Treasury Office | OPEX | OPEX | OPEX | Signed reports
MFVM07 |  |  | 78 | Ratio on financial viability in terms of cost coverage by 30/06/2024 | N/A | Ratio | N/A | 1:02 | 1,47: 02 | 1:02 | N/A | 0:01 | Not Achieved | Unfunded Budget -Insufficient and inadequate limited financial resources | Implementation of the Budget Funding Plan Strategies | Budget & Treasury Office | OPEX | OPEX | OPEX | Signed reports
MFVM08 |  |  | 79 | Ratio on financial viability in terms of outstanding service debtors to revenue by 30/06/2024 | N/A | Ratio | N/A | 1:01 | 0,14: 01 | 1:01 | N/A | 01:0,28, | Not Achieved | Unfunded Budget -Insufficient and inadequate limited financial resources | Implementation of the Budget Funding Plan Strategies | Budget & Treasury Office | OPEX | OPEX | OPEX | Signed reports
MFVM09 |  |  | 80 | Date of approval of 2024/2025 budget by 31/05/2024 | N/A | Date of approval | N/A | Approval of 2023/24 budget by 31/05/2022 | 2023/24 Budget was approved on the 28/05/2022 | Approval of 2024/25 budget by 31/05/2024 | N/A | The 2024/25 budget was approved on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Budget & Treasury Office | OPEX | OPEX | OPEX | Council resolution
MFVM10 |  |  | 81 | Number of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2024 | N/A | Number |  | New Indicator | New Indicator | Twelve (12) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2024 | N/A | Twelve (12) of Progress Reports were submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2024 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | OPEX | Progress Reports, Proof of Submission to Treasury
MFVM11 |  |  | 82 | Date of submission of credible Annual Financial Statements to the Auditor-General by 31/08/2023 | N/A | Date of submission | N/A | Submission of credible Annual Financial Statements to the Auditor-General by 31/08/2022 | Submitted credible Annual Financial Statements to the Auditor-General by 31/10/2022 | Submission of credible Annual Financial Statements to the Auditor-General by 31/08/2023 | N/A | Credible Annual Financial Statements was submitted to the Auditor-General by 31/08/2023 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | OPEX | Proof of submission and Annual Financial Statements
MFVM12 |  | Ensure legislative compliance | 83 | Number of Asset Register developed by 30/06/2024 | N/A | Number of registers | N/A | 1 Asset Register developed by 30/06/2023 | 1 Asset Register developed by 30/06/2023 | 1Asset Register developed by 30/06/2024 | N/A | 1 Asset Register developed by 30/06/2024 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | OPEX | Asset Register
MFVM13 |  |  | 84 | Date of adoption of Finance related policies by Council by 31/05/2024 | N/A | Date of adoption | N/A | Adoption of Finance related policies by Council 31/05/2023 | Adoption of Finance related policies by Council 31/05/2023 | Adoption of Finance related policies by Council 31/05/2024 | N/A | Adoption of Finance related policies by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Budget & Treasury Office | OPEX | OPEX | OPEX | Council Resolution
MFVM14 |  | Monitor the compliance with relevant legislation regarding financial expenditure | 85 | Percentage of reduction of Unauthorised, Irregular, Fruitless and Wasteful Expenditure by 30/06/2024 | N/A | Percentage of reduction | N/A | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2023 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2023 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | N/A | 61% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | Achieved | UIFW relating to prior years was investigated by MPAC and referred to Council for write off. | N/A | All Departments | OPEX | OPEX | OPEX | Signed Reports to Council
MFVM15 |  |  | 86 | Number of Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2024 | N/A | Number | N/A | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2023 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2023 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2024 | N/A | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports were submitted to Council by 30/06/2024 | Achieved | N/A | N/A | All Departments | OPEX | OPEX | OPEX | Signed Reports to Council
MFVM16 | To improve audit opinion | Implement an audit action plan | 87 | Percentage of audit queries raised by the Auditor-General addressed by 30/06/2024 | N/A | Percentage of queries addressed | N/A | 100% of audit queries raised by the Auditor-General addressed by 30/06/2023 | 95% of audit queries raised by the Auditor-General addressed by 30/06/2023 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2024 | N/A | 74% of audit queries raised by the Auditor-General were addressed by 30/06/2024 | Not Achieved | 1, some findings are impacted by the negative cash flow position of the municipality. 2, Other findings will be resolved upon the finalization of the AFS. | 1, Implementation of Revenue Enhancement Strategy, 2, Development of Audit Improvement Strategy. | All Departments | OPEX | OPEX | OPEX | Audit action plan and dashboard report
KPA 6: CROSS CUTTING ISSUES
CCI01 | Efficient & Credible Strategic & Spatial Municipal Planning | Revision of a Credible Integrated Development Plan | 88 | Date of review and adoption of credible integrated development planning by Council by 31/05/2024 | N/A | Date of review and adoption | N/A | Review and adoption of credible integrated development planning by Council by 31/05/2023 | Reviewed and adopted credible integrated development planning on the 28/05/2023 | Review and adoption of credible integrated development planning by Council by 31/05/2024 | N/A | The credible Integrated Development Plan was reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Office of the MM | OPEX | OPEX | OPEX | Council resolution and Integrated development plan
CCI02 | To ensure the implementation of Spatial Development Framework | Improved Spatial Development Framework | 89 | Date of review and adoption of district Spatial Development framework by Council by 30/06/2024 | N/A | Date of review and adoption | N/A | Review and adoption of district Spatial Development framework by Council by 30/06/2023 | Reviewed and adopted district Spatial Development framework by Council on the 28/05/2023 | Review and adoption of district Spatial Development framework by Council by 30/06/2024 | N/A | The District Spatial Development framework was reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Community Services | OPEX | OPEX | OPEX | Council resolution and Spatial Development framework
CCI03 | To ensure sustainable protection and development of the environment | Development and implementation of environmental management Plan | 90 | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2024 | N/A | Date of review and adoption | All | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2023 | Reviewed and Adopted Environmental Management Plan by Council by 28/05/2023 | Review and adoption of Environmental Management Plan provided by Council by 30/06/2024 | N/A | The Environmental Management Plan was reviewed and adopted by Council on the 21/05/2024 | Achieved | Council Meeting was scheduled for the 21 May 2024 for the Adoption of Compliance documents . | N/A | Community Services | OPEX | OPEX | OPEX | Council Resolution and Environmental Management Plan
CCI04 | To create a safety and responsive environment to the community | Attending and responding to disasters and incidents with a district | 91 | Date of Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2024 | N/A | Date of submission | N/A | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2023 | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2023 | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2024 | N/A | Disaster Management Annual Report on Disaster incidents in the prior year has not been submitted to Council by 30 June 2024 | Not Achieved | The information relating to 2023/2024 financial year has been consolidated into Disaster Management Annual Report on Disaster. This Report is currently at a Draft stage. | Disaster Management Annual Report on Disaster incidents in the prior year will be tabled on the next sitting of Council by 30/09/2024 | Community Services | OPEX | OPEX | OPEX | Disaster Management Annual Report, Council Resolution
CCI05 |  |  | 92 | Number Of Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2024 | N/A | Number of Awareness Campaigns | District -wide | Four (4)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2023 | Four (4)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2023 | Four (4)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2024 | N/A | Four (4) Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2024 | Achieved | N/A | N/A | Community Services | OPEX | OPEX | OPEX | Dated Report
CCI06 | To ensure proper communication with the public | Monitor the functioning and efficient of the Municipal Call Centre | 93 | Date of Review of the Call Centre Charter submitted to Council by 30/06/2024 | N/A | Date of review and adoption | N/A | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2023 | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2023 | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2024 | N/A | UTDM Call Centre Charter not submitted to Council by 30/06/2024 | Not Achieved | The Function of the call centre has be re located to water and technical services department | The Call Centre Charter will be submitted to Council quarter 1 of 2024/2025 financial year | Community Services | OPEX | OPEX | OPEX | Call Centre Charter, Council Resolution

## Sheet1 (hidden)
2022/2023 |  | 2023/2024
Achieved | Not Achieved | Achieved | Not Achieved |  | 2022/2023 | 2023/2024
55% | 45%
|  | 62% | 38% | Achieved | 55% | 62%
|  |  |  | Not Achieved | 45% | 38%
Corporate Service
No. of Indicators | 18
No. of Indicators Achieved | 17
No. of Indicators Not Achieved | 1
Water, Sanitation & Technical Services
No. of Indicators | 46
No. of Indicators Achieved | 32
No. of Indicators Not Achieved | 14