## HIGH LEVEL
HIGH LEVEL MUNICIPAL SCORECARD 2025/2026 - MID YEAR REPORT
NAME OF MUNICIPALITY: UTHUKELA DISTRICT MUNICIPALITY | [18 empty] | FINANCIAL YEAR ENDED: 30 JUNE 2026
IDP / SDBIP NO. | Objective | Strategy | Indicator No. | Key Performance Indicator | KPI Measurement | Ward No. | Baseline:2024/2025 |  | 2025/2026 Projections | [9 empty] | Responsible Department | Budget | Budget Spent | Portfolio of Evidence
[7 empty] | Annual Target | Annual Actual | Annual Target | Quarter 1 | Quarter 1 Actual | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 2 Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure
KPA 1: MUNICIPAL TRANFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID01 | To ensure a functional Performance Management System | Implementation of PMS Policy & Framework | 1 | Date of adoption Performance Management System by Council by 30/06/2026 | Date | n/a | Adoption of Performance Management System by Council by 30/05/2025 | Adoption of Performance Management System by Council by 30/05/2025 | Date of Adoption of Performance Management System by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Date of Adoption of Performance Management System by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Council resolution, PMS Policy,Framework and Standard Operating Procedures
MTID02 |  |  | 2 | Number of Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Number | n/a | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2025 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2025 | Number of Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Four (4) Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Two (2) Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Four (4) Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Four (4) Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Four (4) Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Four (4) Departmental quarterly performance reports submitted by departments to the Office of the Municipal Manager within 10 days after the end of each quarter. | Achieved | N/A | N/A | All Departments | OPEX | OPEX | Populated Scorecards ,POE File & Aknowledgement letters
MTID03 |  |  | 3 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2026 | Date | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2025 | Mid-Year Performance Report to the Mayor and Treasuries on the 24/01/2025 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2026 | N/A | N/A | N/A | Date of Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2026 | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Proof of submission and Mid-Year Performance Report
MTID04 |  |  | 4 | Date of submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2025 | Date | n/a | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2024 | Unaudited Annual Performance Report submitted to the Auditor-General on the 31/08/2024 | Date of Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2025 | Date of Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2025 | Unaudited Annual Performance Report was submitted to the Auditor-Genral on 31/08/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Proof of submission and copy of the Annual Performance Report
MTID05 |  |  | 5 | Date of Tabling of Annual Report to Council by 31/03/2026 | Date | n/a | Tabling of Annual Report to Council by 31/03/2025 | Annual Report adopted by Council on 30/03/2025 | Date of Tabling of Annual Report to Council by 31/03/2026 | N/A | N/A | N/A | Date of Tabling of Annual Report to Council by 31/03/2026 | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Council resolution,Copy of the Annual Report
MTID06 |  |  | 6 | Number of formal section 54/56 managers performance reviews conducted by Performance Review Panels by 30/06/2026 | Number | n/a | Two (2) formal section 54/56 managers' performance reviews conducted by performance reviews panels by 30/06/2025 | Two (2) formal section 54/56 managers' performance reviews conducted by performance reviews panels by 30/06/2025 | Two (2) formal section 54/56 managers' performance reviews conducted by Performance Review Panels by 31/03/2026 | N/A | N/A | N/A | Two (2) formal section 54/56 managers' performance reviews conducted by Performance review Panels by 31/03/2026 | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Signed Assessment Reports, Attandance Registers
MTID07 | To ensure fucntional risk and compliance management | Review and adopt risk and compliance governance policies | 7 | Number of risk and Compliance governance Policies adopted by Council by 30/06/2026 | Date | n/a | Review and adoption of risk management framework by Council by 30/06/2025 | Risk management framework reviewed and adopted by Council on the 30/06/2025 | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Council resolution and Policies
MTID08 |  | Ensure functionality of Risk Management Committee | 8 | Number of Risk Committee meetings held by 30/06/2026 | Number meetings | n/a | Four (4) Risk Committee meetings held by 30/06/2025 | Four (4) Risk Committee meetings held by 30/06/2025 | Four (4) Risk Committee meetings held by 30/06/2026 | One (1) Risk Committee meetings held by 30/09/2025 | Risk Committee meeting was not held by 30/09/2025 | One (1) Risk Committee meetings held by 31/12/ 2025 | One (1) Risk Committee meetings held by 31/03/2026 | One (1) Risk Committee meetings held by 30/06 /2026 | Zero (0) Risk Committee meetings held by 31/12/ 2025 | Not Achieved | The External Risk Chairperson was appointed in November 2025. | The Risk Committee meeting will be held in Quarter 3. | Office of the MM | OPEX | OPEX | Notice,Agenda, Attandance Register, Minutes
MTID09 | To Improve organisational Capacity | Review of organisational structure | 9 | Date of organizational structure reviewed and adopted by Council by 31/05/2026 | Date | n/a | Review and adoption of organizational structure by Council by 31/05/2025 | Organizational structure reviewed and adopted by Council by 31/05/2025 | Date of Review and adoption of organizational structure by Council by 31/05/2026 | N/A | N/A | N/A | N/A | Date of Review and adoption of organizational structure by Council by 31/05/2026 | N/A | N/A | N/A | N/A | Corporate Services | OPEX | OPEX | Council Resolution,Organizational structure
MTID10 |  | Ensure implementation of Employment equity plan | 10 | Number of people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 31/12/2025 | Number | n/a | 1 people from employment equity target groups employed in the three (3)highest levels of management in compliance with approved equity plan by 30/06/2025 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2025 | Six(6) people from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 31/12/2025 | Two (2) people from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/09/2025 | Two (2) people from employment equity target groups were employed in the three (3) highest levels of management in compliance with approved equity plan by 30/09/2025 | Two (2) people from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 31/12/2025 | N/A | N/A | One (1) people from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 31/12/2025 | Not Achieved | 1 Position of General Manager Community Services was filled. Other positions have not been filled. | The Target will be revised to align to the Planning and Financial Position of the Municipality | Corporate Services | OPEX | OPEX | Employment Equity Plan and appointment letters
MTID11 |  | Implementation of Workplace Skills Plan | 11 | Percentage of budget spent in the implementation of Workplace Skills Plan by 30/06/2026 | Percentage | n/a | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2025 | Fifty Five (55%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2025 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2026 | Twenty (25%) of budget spent in the implementation of Workplace Skills Plan by 30/09/2025 | 2% of budget spent in the implementation of Workplace Skills Plan by 30/09/2025 | Fifty (50%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2025 | Seventy Five (75%) of budget spent in the implementation of Workplace Skills Plan by 31/03/2026 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2026 | Seventy (70%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2025 | Achieved | N/A | N/A | Corporate Services | OPEX | OPEX | Financial System Print Out
MTID12 |  |  | 12 | Number of training reports submitted to Council by 30/06/2026 | Number | n/a | 4 Training reports submitted to Council by 30/06/2025 | 4 Training reports submitted to Council by 30/06/2025 | 4 Training reports submitted to Council by 30/06/2026 | 1 Training report submitted to Council by 30/09/2025 | 1 Training report was not submitted to Council by 30/09/2025 | 1 Training report submitted to Council by 31/12/2025 | 1 Training report submitted to Council by 31/03/2026 | 1 Training report submitted to Council by 30/06/2026 | 1 Training report submitted to Council by 31/12/2025 | Achieved | N/A | N/A | Corporate Services | OPEX | OPEX | Signed Training Report,Council Resolution
MTID13 | To ensure an effective and efficient HR systems that addresses Human resources within the municipality | Review and adoption of HR related policies | 13 | Date of review and adoption of HR related policies by Council by 30/06/2026 | Date | n/a | Review and adoption of HR related policies by Council by 30/06/2025 | HR related policies reviewed and adopted by Council on the 30/06/2025 | Date of Review and adoption of HR related policies by Council by 30/06/2026 | N/A | N/A | N/A | Date of Review and adoption of HR related policies by Council by 30/06/2026 | n/a | N/A | N/A | N/A | N/A | Corporate Services | OPEX | OPEX | HR related policies & Council Resolution
MTID14 | To improve Information and Communication Technology through implementation of ICT policies | Development and review of ICT policies | 14 | Number of ICT Policies developed and reviewed by the Council by the 30th June 2026 | Number | n/a | Ten (10) ICT Policy reviewed by Council by 30/06/2025 | Ten (10) ICT Policy reviewed by Council by 30/06/2025 | Ten (10) ICT Policy reviewed by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Ten (10) ICT Policy reviewed by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Corporate Services | OPEX | OPEX | Council Resolution,ICT Plicies
MTID15 | Ensure an effective and functional Fleet Services | Conducting Comprehensive reporting of Fleet Management Services | 15 | Number of Comprehensive Fleet Reports submitted to Council by 30/06/2026 | Number | n/a | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2025 | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2025 | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2026 | One (1) of Comprehensive Fleet Reports submitted to Council by 30/09/2025 | One (1) of Comprehensive Fleet Report was submitted to Council by 30/09/2025 | One (1) of Comprehensive Fleet Reports submitted to Council by 31/12/2025 | One(1) of Comprehensive Fleet Reports submitted to Council by 31/03/2026 | One (1) of Comprehensive Fleet Reports submitted to Council by 20/06/2026 | One (1) of Comprehensive Fleet Reports submitted to Council by 31/12/2025 | Achieved | N/A | N/A | Corporate Services | OPEX | OPEX | Signed Comprehensive Fleet Report,Council Resolution
MTID16 | To ensure effective and efficient internal and external communication strategy. | Review and Impelemtation of adopted Communication Strategy | 16 | Date of review and adoption of communication strategy by Council by 30/06/2026 | Date | n/a | Review and adotion of communication strategy by Councl by 30/06/2025 | Communication strategy was reviewed and adopted by Council on 26/06/2025 | Date of Review and adoption of communication strategy by Councl by 30/06/2026 | N/A | N/A | N/A | N/A | Date of Review and adoption of communication strategy by Councl by 30/06/2026 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Communication Strategy & Council Resolution
MTID17 | Improve communications with external Stakeholders | Development of Municipal Communication Strategy | 17 | Number of Municipal Newsletters published for each financial year by 30/06/2026 | Number | n/a | Four (4) Municipal newsletters published by 30/06/2025 | Four (4) Municipal newsletters published by 30/06/2025 | Four (4) Municipal newsletters published by 30/06/2026 | One (1) Municipal newsletters published by 30/09/2025 | One (1) Municipal newsletters was published by 30/09/2025 | One (1) Municipal newsletters published by 31/12/2025 | One (1) Municipal newsletters published by 31/03/2026 | One (1) Municipal newsletters published by 30/06/2026 | One (1) Municipal newsletters published by 31/12/2025 | Achieved | N/A | N/A | Office of the MM | OPEX | OPEX | Municipal newsletters,Proof of Publication
MTID18 | To report & monitor Service Delivery | Submission of quarterly reports to COGTA | 18 | Number of Circular 88 reports submitted to Provincial COGTA by 30/06/2026 | Number | n/a | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2025 | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2025 | 4 Circular 88 reports submitted to Provincial COGTA by 30/06/2026 | 1 Circular 88 reports submitted to Provincial COGTA by 30/09/2025 | 0 Circular 88 reports submitted to Provincial COGTA by 30/09/2025 | 1 Circular 88 reports submitted to Provincial COGTA by 31/12/2025 | 1 Circular 88 reports submitted to Provincial COGTA by 31/03/2026 | 1 Circular 88 reports submitted to Provincial COGTA by 30/06/2026 | 1 Circular 88 reports submitted to Provincial COGTA by 31/12/2025 | Achieved | N/A | N/A | Office of the MM | OPEX | OPEX | Circular 88 reports , Proof of submission
MTID19 | To improve the municipal Audit opinion | Effective Audit and Performance Committee | 19 | Number of Audit and Performance Committee meetings held by 30/06/2026 | Number | n/a | 4 Audit and Performance Committee meetings held by 30/06/2025 | 4 Audit and Performance Committee meetings held by 30/06/2025 | 4 Audit and Performance Committee meetings held by 30/06/2026 | 1 Audit and Performance Committee meeting held by 30/09/2025 | 2 Audit and Performance Committee meetings were held on 30/07/2025 and 27/08/2025 | 1 Audit and Performance Committee meeting held by 31/12/2025 | 1 Audit and Performance Committee meeting held by 31/03/2026 | 1 Audit and Performance Committee meeting held by 30/06/2026 | 1 Audit and Performance Committee meeting held on the 19/11/2025 | Achieved | N/A | N/A | Office of the MM | 372858.34 | 51285.03 | Minutes with attendance registers
MTID20 |  |  | 20 | Percentage of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 30/06/2026 | Percentage |  | New Indicator | New Indicator | Hundred (100%) of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 30/06/2026 | Hundred (100%) of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 30/09/2025 | Zero 0%) of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 30/09/2025 | Hundred (100%) of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 31/12/2025 | Hundred (100%) of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 31/03/2026 | Hundred (100%) of Audit and Performance Committee Resolutions presented to Council Actioned and Resolved by Management by 30/06/2026 |  |  |  |  | Office of the MM |  |  | Resolutions Audit Log Status Report as per the approved MPAC Workplan
MTID21 |  | Oversight meetings held | 21 | Number of MPAC meetings convened by 30/06/2026 | Number | n/a | 4 MPAC meetings convened by 30/06/2025 | 4 MPAC meetings convened by 30/06/2025 | 4 MPAC meetings convened by 30/06/2026 | 1 MPAC meeting convened by 30/09/2025 | 1 MPAC meeting convened by 25/08/2025 | 1 MPAC meeting convened by 31/12/2025 | 1 MPAC meeting convened by 31/03/2026 | MPAC meeting convened by 30/03/2026 | 1 MPAC meeting convened by 22/10/2025 | Achieved | N/A | N/A | Office of the MM | OPEX | OPEX | Minutes with attendance registers
MTID22 |  |  | 22 | Percentage of Deliverables Achieved by the MPAC as per the Approved Plan by 30/06/2026 | Percentage |  | New Indicator | New Indicator | Hundred (100%) of Deliverables Achieved by the MPAC as per the Approved Plan by 30/06/2026 | Hundred (100%) of Deliverables Achieved by the MPAC as per the Approved Plan by 30/09/2025 | Zero (0%) of Deliverables Achieved by the MPAC as per the Approved Plan by 30/09/2025 | Hundred (100%) of Deliverables Achieved by the MPAC as per the Approved Plan by 31/12/2025 | Hundred (100%) of Deliverables Achieved by the MPAC as per the Approved Plan by 31/03/2026 | Hundred (100%) of Deliverables Achieved by the MPAC as per the Approved Plan by 30/06/2026 |  |  |  |  | Office of the MM | OPEX | OPEX | Approved Work Plan by Council, MPAC Status Workplan Report
KPA2: BASIC SERVICE DELIVERY
BSD01 | To provide infrastructure and sustainable basic services | Provide community water supply | 23 | Number of Households provided with water to eradicate backlog by 31/03/2026 | Number | 3,4,14 | New Indicator | New Indicator | 745 of Households provided with water to eradicate backlock by 31/03/2026 Erf connection (Wembezi) -400 Yard connection (Vimbukhalo 3) - 210 Yard connections(Vimbukhalo 4)-135 | 345 of Households provided with water to eradicate backlock by 30/09/2025 Yard connections(Vimbukhalo 3)- 210 Yard connections(Vimbukhalo 4)-135 | 0 of Households provided with water to eradicate backlock by 30/09/2025 Yard connections(Vimbukhalo 3)- 0 Yard connections(Vimbukhalo 4)-0 | N/A | 400 of Households provided with water to eradicate backlock by 31/03/2026 Erf connection(Wembezi) -400 | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 15000000 | 848040.3 | Signed Engineers Report, Beneficiary listing and Happy letters
BSD02 |  |  | 24 | Date of site establishment at Wembezi WCDM by 31/12/2025 | Date | 6 | New Indicator | New Indicator | Date of site establishment at Wembezi WCDM by 31/12/2025 | Appointment of Contractor at Wembezi WCDM by 30/09/2025 | Contractor appointed on 18/06/2025. Contractor commenced with Site Establishment on 05 August 2025 | Date of site establishment at Wembezi WCDM by 31/12/2025 | N/A | N/A | Site establishment achieved at Wembezi WCDM by 31/12/2025 | Achieved | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD03 |  |  | 25 | Number of KM's of gravity main pipeline constructed at Wembezi WCDM by 31/03/2026 | Kilometers | 6 | New Indicator | New Indicator | 1.95 KM's of gravity main pipeline constructed at Wembezi WCDM by 31/03/2026 | N/A | N/A | 0.95 KM's of gravity main pipeline to be constructed at Wembezi WCDM by 31/12/2025 | 1 KM's of gravity main pipeline to be constructed at Wembezi WCDM by 31/03/2026 | n/a | 0 KM's of gravity main pipeline to be constructed at Wembezi WCDM by 31/12/2025 | Not Achieved | Slow progress from the contractor , delays in submission of contractual documents | Contractor was issued with a slow progress letter.Contractor was instructed to submit revised program and methodology detailing the resources to be utilized on site | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD04 |  |  | 26 | Installation of H/H domestic meters in Csection-Subzone 3 constructed at Ezakheni WCDM: Phase 2 by 31/12/2025 | Kilometers | 5 | New Indicator | New Indicator | 346 H/H domestic meters Installed at Csection-Subzone 3 constructed at Ezakheni WCDM: Phase 2 by 31/12/2025 | 174 H/H domestic meters Installed at Csection-Subzone 3 constructed at Ezakheni WCDM: Phase 2 by by 30/09/2025 | 0 H/H Domestic meters was completed | 172 H/H domestic meters Installed at Csection-Subzone 3 constructed at Ezakheni WCDM: Phase 2 by by 31/12/2025 | N/A | n/a | (0) H/H domestic meters Installed at Csection-Subzone 3 constructed at Ezakheni WCDM: Phase 2 by 31/12/2025 | Not Achieved | Contractor Suspended works due to delays in payments, | The Municipality has successfully resolved the outstanding payments owed to the contractor. Consequently, the contractor has expedited the work on site, and an extension of time has been granted to facilitate the completion of the remaining scope of work | Water, Sanitation & Technical Services | 7000000 | 3759184.83 | Signed Engineers Report
BSD05 |  |  | 27 | Number of Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) installed at Ezakheni WCDM: Phase 2 by 31/12/2025 | Number | 5 | 07 Bulk meters chamber (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/06/2025 | 07 Bulk meters chamber (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/06/2025 | 141 Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) installed at Ezakheni WCDM: Phase 2 by 31/12/2025 | 69 Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 30/09/2025 | 6 Chambers completed | 72 Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) to be installed at Ezakheni WCDM: Phase 2 by 31/12/2025 | N/A | n/a | (6) Bulk meter chambers (Rising main from Rose Hill Reservoir to high Tower) installed at Ezakheni WCDM: Phase 2 by 31/12/2025 | Not Achieved | Contractor Suspended works due to delays in payments, | The Municipality has successfully resolved the outstanding payments owed to the contractor. Consequently, the contractor has expedited the work on site, and an extension of time has been granted to facilitate the completion of the remaining scope of work | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD06 |  |  | 28 | Number of kilometres of Reticulation(HDPE) constructed at Fitty Park Community water project: Phase 2 by 30/09/2025 | Number | 7, 28, 30 &31 | 1,222 Kilometres of reticulation (HDPE Pipeline and PVC Pipeline) pipelines constructed at Fitty Park Community Water Project by 30/06/2025 | 1,222 Kilometres of reticulation (HDPE Pipeline and PVC Pipeline) pipelines constructed at Fitty Park Community Water Project by 30/06/2024 | 1.4 km of reticulation (HDPE )pipeline constructed at Fitty Park Community Water Project by 30/09/2025 | 1.4 km of reticulation (HDPE )pipeline to be constructed at Fitty Park Community Water Project by 30/09/2025 | 700m of pipeline was constructed and installed. | N/A | N/A | N/A | 0.7 km of reticulation (HDPE )pipeline constructed at Fitty Park Community Water Project by 31/12/2025 | Not achieved | Contractor Suspended works due to delays in payments, and approval of crossings application from department of transport | The municipality successfully settled the outstanding payments and crossings application was approved on …. | Water, Sanitation & Technical Services | 20850000 | 1120691.46 | Signed Engineers Report
BSD07 |  |  | 29 | Date of Completion of Fitty Park Community water project Phase 2 by 30/09/2025 | Number | 7, 28, 30 &31 | New Indicator | New Indicator | Date of Completion of Fitty Park Community water project Phase 2 by 30/09/2025 | Date of Completion of Fitty Park Community water project Phase 2 by 30/09/2025 | Completion was not reached for Fitty Park Community water project Phase 2 by 30/09/2025 | N/A | N/A | N/A | Date of Completion of Fitty Park Community water project Phase 2 by 30/12/2025 | Not Achieved | Contractor Suspended works due to delays in payments, and approval of crossings application from department of transport | The municipality successfully settled the outstanding payments and crossings application was approved on …. | Water, Sanitation & Technical Services |  |  | Pratical Completion Certificate,Signed Engineers Report
BSD08 |  |  | 30 | Number of VIP toilets constructed by 31/03/2026 | Number | District -wide | 2000 VIP toilets constructed by 30/06/2025 | 2000 VIP toilets constructed by 30/06/2025 | 1100 VIP toilets constructed by 31/03/2026 | 400 VIP toilets constructed by 30/09/2025 | 401 VIP toilets were completed | 450 VIP toilets constructed by 31/12/2025 | 250 VIP toilets constructed by 31/03/2026 | N/A | 406 VIP toilets constructed by 31/12/2025 | Achieved | Delays in community hand overs, and inclement weather conditions | UTDM to prioritize hand overs of the outstanding wards. | Water, Sanitation & Technical Services | 20042687.81 | 2472496.66 | Signed Engineers Report, Beneficiary listing and Happy letters
BSD09 |  |  | 31 | Number of Reserviors constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 and 4 by 30/09/2025 | Number | 2,3 & 14 | One (1) Resevoir constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 &4 by 30/06/2025 | One (1) Resevoir constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 &4 by 30/06/2025 | Two (2) Resevoir constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 &4 by 30/09/2025 | Two (2) Resevoir to be constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3&4 by 30/09/2025 | One (1) constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3&4 by 30/09/2025 | N/A | N/A | N/A | One (1) Resevoir constructed at Okhahlamba LM (Ward 2,3 & 14) Vimbukhalo Groundwater programme 3 &4 by 31/12/2025 | Not achieved | Slow progress from the Contractor due to financial constraints | Intention to terminate was issued to the Contractor. | Water, Sanitation & Technical Services | 20500000 | 8623120.93 | Signed Engineers Report
BSD10 |  |  | 32 | Number of bulk pipeline(AC pipeline) constructed at Steadville WCDM by 30/09/2025 | Number | 9, 20 & 21 | 8,029 kilometres of bulk pipeline constructed at Steadville WCDM by 30/06/2025 | 8,029kilometres of bulk pipeline constructed at Steadville WCDM by 30/06/2025 | 0.545 bulk pipeline(AC pipeline) constructed at Steadville WCDM by 30/09/2025 | 0.545 Number of bulk pipeline(AC pipeline)to be constructed at Steadville WCDM by 30/09/2025 | 1,752 km was completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 15000000 | 62005837.54 | Signed Engineers Report
BSD11 | To provide infrastructure and sustainable basic services | Provide community with water supply | 33 | Number of installation of bulk metering chambers at Steadville WCDM by 30/09/2025 | Number | 9, 20 & 21 | (5) installation of bulk metering at Steadville by 30/06/2025 | (5) installation of bulk metering at Steadville by 30/06/2025 | 9 bulk meters chambers installed at Steadville WCDM by 30/09/2025 | 9 bulk meters chambers to be installed at Steadville WCDM by 30/09/2025 | 0 chambers completed | N/A | N/A | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD12 |  |  | 34 | Number of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/09/2025 | Number | 21 & 22 | 3,266 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2025 | 3,266 kilometres of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2025 | 0.605 km of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/09/2025 | 0.605 km of bulk pipeline to be constructed at Ladysmith AC pipeline replacement by 30/09/2025 | 0,448 km was completed | N/A | N/A | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 18000000 | 1205401.12 | Signed Engineers Report
BSD13 |  |  | 35 | Number of bulk meter chambers installed at Ladysmith AC pipeline replacement by 30/09/2025 | Number | 21 & 22 | (5) installation of bulk metering at Ladysmith AC pipeline replacement by 30/06/2025 | (5) installation of bulk metering at Ladysmith AC pipeline replacement by 30/06/2025 | (8) bulk meter chambers installed at Ladysmith AC pipeline replacement by 30/09/2025 | (8) bulk meter chambers to be installed at Ladysmith AC pipeline replacement by 30/09/2025 | 6 Chambers completed | N/A | N/A | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD14 |  |  | 36 | Number of sewer and water networks refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/09/2025 | Number | 20,21 | New Indicator | New indicator | (2) of sewer and water network to be refurbished at Kwanobamba/Ezitendeni Refurbishment of Water & Sewer Networks Project by 30/09/2025 | (2) of sewer and water network to be refurbished at Kwanobamba/Ezitendeni Refurbishment of Water & Sewer Networks Project by 30/09/2025 | 0 of sewer and water network to be refurbished at Kwanobamba/Ezitendeni Refurbishment of Water & Sewer Networks Project by 30/09/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 20500000 | 587352.83 | Signed Engineers Report
BSD15 |  |  | 37 | Number of sewer pumpstation refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/09/2025 | Number | 20,21 | one (1) of sewer pumpstation refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/06/2025 | one (1) of sewer pumpstation refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/06/2025 | one (1) of sewer pumpstation refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/09/2025 | one (1) of sewer pumpstation refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/09/2025 | one (1) of sewer pumpstation refurbished at Kwanobamba/Ezitendeni Refurbishment of Water and Sewer Networks Project by 30/09/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD16 |  |  | 38 | Date of Site establishment at Kwanobamba Ezitendeni -Abstraction Tower Water Supply by 30/06/2026 | Date | 21 | New Indicator | New Indicator | Date Site establishment at Kwanobamba Ezitendeni -Abstraction Tower Water Supply by 30/06/2026 | N/A | N/A | N/A | N/A | Site establishment at Kwanobamba Ezitendeni -Abstraction Tower Water Supply by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 17000000 | 587352.83 | Signed Engineers Report
BSD17 |  |  | 39 | Date of Site establishment at Kwanobamba Ezitendeni CBD sewer network by 30/06/2026 | Date | 20,21 | New Indicator | New Indicator | Date of Site establishment at Kwanobamba Ezitendeni CBD sewer network by 30/06/2026 | N/A | N/A | N/A | N/A | Date of site establisment at Kwanobamba Ezitendeni CBD sewer network by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD18 |  |  | 40 | Date of Completion of designs at Kwanobamba Ezitendeni CBD sewer network by 31/12/2025 | Date | 20,21 | New Indicator | New Indicator | Date Completion of designs at Kwanobamba Ezitendeni CBD sewer network by 31/12/2025 | N/A | N/A | Completion of designs at Kwanobamba Ezitendeni CBD sewer network by 31/12/2025 | N/A | n/a | Completion of designs not completed at Kwanobamba Ezitendeni CBD sewer network by 31/12/2025 | Not Achieved | Design development not approved due to number or sewee pumpstation in the design | PMU to prioritize the approval of designs | Water, Sanitation & Technical Services | 15000000 | 587352.83 | Signed Engineers Report
BSD19 |  |  | 41 | Date of site establishment at Loskop Abstraction WTW by 30/09/2025 | Number | 3 | New Indicator | New Indicator | Date of site establishment at Loskop Abstraction WTW by 30/09/2025 | Date of site establishment at Loskop Abstraction WTW by 30/09/2025 | Date of site establishment not reached at Loskop Abstraction WTW by 30/09/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 56315763 | 8176681.16 | Signed Engineers Report
BSD20 |  |  | 42 | Killometres of bulk pipeline constructed at Loskop Abstraction WTW by 31/12/2025 | Killometres | 3 | 0,14 Kilometres of bulk pipeline at Loskop Abstraction WTW by 30/06/2024 | 0,14 Kilometres of bulk pipeline at Loskop Abstraction WTW by 30/06/2024 | 0,076 KM's of bulk pipeline constructed at Loskop Abstraction WTW by 31/12/2025 | N/A | N/A | 0,076 KM's of bulk pipeline to be constructed at Loskop Abstraction WTW by 31/12/2025 | N/A | N/A | (0)KM's of bulk pipeline not structed at Loskop Abstraction WTW by 31/12/2025 | Not Achieved | Appointment of Contractor not achieved | SCM to facilitate the award of the Contractor | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD21 |  |  | 43 | Number of abstraction sump(M&E) installed at Loskop Abstraction WTW by 31/03/2026 | Number | 3 | New Indicator | New Indicator | (1)of abstraction sump(M&E) to be installed at Loskop Abstraction WTW by 31/03/2026 | N/A | N/A | N/A | (1)of abstraction sump(M&E) to be installed at Loskop Abstraction WTW by 31/03/2026 | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD22 |  |  | 44 | Date of site establishment at Amagwe Phase 9B1 by 30/09/2025 | Date | 1 | New Indicator | New Indicator | Date of site establishment at Amagwe Phase 9B1 by 30/09/2025 | Date of site establishment at Amagwe Phase 9B1 by 30/09/2025 | Date of site establishment not reached at Amagwe Phase 9B1 by 30/09/2025 | N/A | n/a | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 56315763 | 55246.85 | Signed Engineers Report
BSD23 |  |  | 45 | Number of pipeline constructed at Amagwe Phase 9B1 by 30/06/2026 | Number | 1 | New Indicator | New Indicator | (3) KM's of pipeline constructed at Amagwe Phase 9B1 by 30/06/2026 | N/A | N/A | N/A | N/A | N/A | (0) KM of pipeline constructed at Amagwe Phase 9B1 by 31/12/2025 | Not achieved | The late appointment of the Contractor resulted in delays in the construction work | The Contractor was appointment on the 4th of September 2025. Contractor to revise the program of works | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD24 |  |  | 46 | Date of site establishment at Amagwe Phase 9B2 by 30/09/2025 | Date | 1 | New Indicator | New Indicator | Date of site establishment at Amagwe Phase 9B2 by 30/09/2025 | Date of site establishment at Amagwe Phase 9B2 by 30/09/2025 | Date of site establishment not reached at Amagwe Phase 9B2 by 30/09/2025 | n/a | n/a | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD25 |  |  | 47 | Number of pipeline constructed at Amagwe Phase 9B2 by 30/06/2026 | Date | 1 | New Indicator | New Indicator | 1.7 KM's of pipeline constructed at Amagwe Phase 9B2 by 30/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD26 |  |  | 48 | Number of handpumps to be equipped at Ekuvukeni Groundwater by 31/12/2025 | Number | 31 | New Indicator | New Indicator | 5 handpumps to be at equipped Ekuvukeni Groundwater by 31/12/2025 | 1 handpumps to be at equipped Ekuvukeni Groundwater by 30/09/2025 | 0 handpumps equipped Ekuvukeni Groundwater by 30/09/202 | 4 handpumps to be at equipped Ekuvukeni Groundwater by 31/12/2025 | N/A | N/A | 0 handpumps equipped at Ekuvukeni Groundwater by 31/12/2025 | Not Achieved | Change of scope and social challenges | Change of scope that was approved by the Municipality due to water quality results. Extension of reticulation network and standpipes for the equipped production boreholes | Water, Sanitation & Technical Services | 18000000 | 4857523.99 | Signed Engineers Report
BSD27 |  |  | 49 | Number of production boreholes equipped at Ekuvukeni Groundwater by 30/09/2025 | Number | 31 | New Indicator | New Indicator | 2 production boreholes equipped at Ekuvukeni Groundwater by 30/09/2025 | 2 production borehole to be equipped atEkuvukeni Groundwater by 30/09/2025 | 0 production borehole equipped atEkuvukeni Groundwater by 30/09/2025 | n/a | N/A | 3 production boreholes to be equipped atEkuvukeni Groundwater by 30/06/2025 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD28 |  |  | 50 | Number of 1.0 ML GMS Reservoir completed at Ntabamhlophe by 30/09/2025 | Number | 2,3,14 | New Indicator | New Indicator | One (1) 1.0 ML GMS Reservoir completed at Ntabamhlophe by 30/09/2025 | One (1) 1.0 ML GMS Reservoir completed at Ntabamhlophe by 30/09/2025 | Zero(0) 1.0 ML GMS Reservoir completed at Ntabamhlophe by 30/09/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 10000000 | 0 | Signed Engineers Report
BSD29 |  |  | 51 | Date of Completion of Ntabamhlophe Water Supply Scheme by 31/12/2025 | Number | 2,3,14 | New Indicator | New Indicator | Date of Completion of Ntabamhlophe Water Supply Scheme by 31/12/2025 | N/A | N/A | N/A | N/A | N/A | Date of Completion not completed at Ntabamhlophe Water Supply Scheme by 31/12/2025 | Not Achieved | Contractor was terminated. Delays in the appointment of the new contractor | SCM processes to source a new Contractor to be prioritised | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD30 |  |  | 52 | Date of appointment of Contractor at Kwanobamba Ezitendeni :Abstraction Tower by 31/03/2026 | Date | 21 | New Indicator | New Indicator | Date of appointment of Contractor at Kwanobamba Ezitendeni :Abstraction Tower by 31/03/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 20500000 | 587352.83 | Signed Engineers Report
BSD31 |  |  | 53 | Number of abstration tower at Kwanobamba Ezitendeni by 30/06/2026 | Number | 21 | New Indicator | New Indicator | (1) of abstraction tower to be constructed at Kwanobamba Ezitendeni by 30/06/2026 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD32 |  |  | 54 | Number of PRV's refurbished at Water & Sanitation Refurbs Phase 3 by 30/09/2025 | Number | 3,4,5 | New Indicator | New Indicator | 7 of PRV's at Water & Sanitation Refurbs Phase 3 by 30/09/2025 | 7 of PRV's at Water & Sanitation Refurbs Phase 3 by 30/09/2025 | 7 of PRV's at Water & Sanitation Refurbs Phase 3 were completed | n/a | n/a | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 10300000 | 2376820 | Signed Engineers Report
BSD33 |  |  | 55 | Number of sewer pump stations refurbished at Water and Sanitation Refurbs Phase 3 Project by 30/09/2025 | Number | District -wide | New Indicator | New Indicator | 5 sewer pump stations to be refurbished at Water and Sanitation Refurbs Phase 3 Project by 30/09/2025 | 5 sewer pump stations to be refurbished at Water and Sanitation Refurbs Phase 3 Project by 30/09/2025 | 5 sewer pump stations to be refurbished at Water and Sanitation Refurbs Phase 3 were compeleted | N/A | n/a | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD34 |  |  | 56 | Date of Appointment of Contractor at Steadville WCDM Work package 2 by 31/12/2025 | Date | 9,20 & 21 | New Indicator | New Indicator | Date of Appointment of Contractor at Steadville WCDM Work Package 2 by 31/12/2025 | N/A | N/A | Date of Appointment of Contractor at Steadville WCDM Work package 2 by 31/12/2025 | n/a | n/a | Date of Appointment of Contractor not completed at Steadville WCDM Work package 2 by 31/12/2025 | Not Achieved | Delays encoutered in the approval of the business plan | Awaiting for approval from the funder | Water, Sanitation & Technical Services | 15000000 | 6205837.54 | Signed Engineers Report
BSD35 |  |  | 57 | Number of bulk pipeline(AC pipeline) constructed at Steadville WCDM Work package 2 by 30/06/2025 | Number | 9,20 & 21 | New Indicator | New Indicator | 4.8 KM's of bulk pipeline(AC pipeline) constructed at Steadville WCDM -Work package 2 by 30/06/2026 | N/A | N/A | 0.85 KM's of bulk pipeline(AC pipeline) to be constructed at Steadville WCDM-Work package 2 by 31/12/2025 | 1.25 KM's of bulk pipeline(AC pipeline) to be constructed at Steadville WCDM-Work package 2 by 31/03/2026 | 2.7 KM's of bulk pipeline(AC pipeline)to be constructed at Steadville WCDM-Work package 2 by 30/06/2026 | (0) KM's of bulk pipeline(AC pipeline) constructed at Steadville WCDM-Work package 2 by 31/12/2025 | Not Achieved | Delays encoutered in the approval of the business plan | Awaiting for approval from the funder | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD36 |  |  | 58 | Number of bulk pipeline constructed at Ladysmith AC -Work package 2 pipeline replacement by 30/06/2026 | number | 21,22 | New Indicator | New Indicator | 4.050 KM's of bulk pipeline constructed at Ladysmith AC -Work package 2 pipeline replacement by 30/06/2026 | N/A | N/A | 0.55 KM's of bulk pipeline to be constructed at Ladysmith AC -Work package 2 pipeline replacement by 31/12/2025 | 0.95 KM's of bulk pipeline to be constructed at Ladysmith AC -Work package 2 pipeline replacement by 31/12/2025 | 2.55 KM's of bulk pipeline to be constructed at Ladysmith AC -Work package 2 pipeline replacement by 30/06/2026 | (0) KM's of bulk pipeline to be constructed at Ladysmith AC -Work package 2 pipeline replacement by 31/12/2025 | Not Achieved | Delays encoutered in the approval of the business plan | Awaiting for approval from the funder | Water, Sanitation & Technical Services | 18000000 | 1205401.13 | Signed Engineers Report
BSD37 |  |  | 59 | Number of installation of bulk metering chambers at Ladysmith AC-Work package 2 pipeline replacement by 30/06/2026 | Number | 21,22 | New Indicator | New Indicator | 21 installation of bulk metering chambers at Ladysmith AC-Work package 2 pipeline replacement by 30/06/2026 | N/A | N/A | n/a | 9 bulk metering chambers to be installed at Ladysmith AC-Work package 2 pipeline replacement by 31/03/2026 | 9 bulk metering chambers to be installed at Ladysmith AC-Work package 2 pipeline replacement by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD38 |  |  | 60 | Date of Appointment of Contractor at Ekuvukeni Groundwater WCDM -ward 33 by 30/09/2025 | Date | 33 | New Indicator | New Indicator | Date of Appointment of Contractor at Ekuvukeni Groundwater WCDM -ward 33 by 30/09/2025 | Date of Appointment of Contractor at Ekuvukeni Groundwater WCDM -ward 33 by 30/09/2025 | The contractor was appointed on the 4th of September 2025 | N/A | N/A | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 18000000 | 4857523.99 | Signed Engineers Report
BSD39 |  |  | 61 | Number of kilometers pipeline at Ekuvukeni Groundwater WCDM -ward 33 by 30/06/2026 | Kilometers | 33 | New Indicator | New Indicator | 3 KM's pipeline at Ekuvukeni Groundwater WCDM -ward 33 by 30/06/2026 | N/A | N/A | N/A | 1.2 kilometers pipeline at Ekuvukeni Groundwater WCDM -ward 33 by 31/03/2026 | 1.8 kilometers pipeline at Ekuvukeni Groundwater WCDM -ward 33 by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD40 |  |  | 62 | Date of Appointment of Contractor at Bergville WTW for upgrading of water supply Phase 2 by 30/09/2025 | Date | 11 | New Indicator | New Indicator | Date of Appointment of Contractor at Bergville WTW for upgrading of water supply Phase 2 by 30/09/2025 | Date of Appointment of Contractor at Bergville WTW for upgrading of water supply Phase 2 by 30/09/2025 | The contractor was appointed on the 4th of September 2025 | N/A | N/A | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 10076098 | 1639735.53 | Signed Engineers Report
BSD41 |  |  | 63 | Number of kilometres of clear water rising main constructed at Upgrade of Bergville WTW water supply Phase 2 by 30/06/2026 | Kilometers | 11 | New Indicator | New Indicator | 2.88 KM's of clear water rising main constructed at Upgrade of Bergville WTW water supply Phase 2 by 30/06/2026 | N/A | N/A | 0.96 KM's of clear water rising mainto be constructed at Upgrade of Bergville WTW water supply Phase 2 by 30/09/2025 | 1.44 KM's of clear water rising main to be constructed at Upgrade of Bergville WTW water supply Phase 2 by 31/12/2025 | 0.48 KM's of clear water rising main to be constructed at Upgrade of Bergville WTW water supply Phase 2 by 31/12/2025 | 0 KM's of clear water rising maintenance not constructed at Upgrade of Bergville WTW water supply Phase 2 by 31/12/2025 | Not Achieved | Late appointment of project CLO, inclement weather conditions | CLO was appointed on the 20 November 2025 | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD42 |  |  | 64 | Date of Appointment of Contractor at Bergville AC Pipeline replacement by 31/03/2026 | Date | 11 | New Indicator | New Indicator | Date of Appointment of Contractor at Bergville AC Pipeline replacement by 31/03/2026 | N/A | N/A | N/A | Date of Appointment of Contractor at Bergville AC Pipeline replacement by 31/03/2026 | n/a | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 15000000 |  | Signed Engineers Report
BSD43 |  |  | 65 | Number of kilometers constructed at Bergville AC Pipeline replacement by 30/06/2026 | Number | 11 | New Indicator | New Indicator | 6 KM's of UPVC pipeline at constructed Bergville AC Pipeline replacement by 30/06/2026 | N/A | N/A | N/A | 2.5 KM's of UPVC pipeline to be constructed at Bergville AC Pipeline replacement by 31/03/2026 | 3.5 KM's of UPVC pipeline to be constructed at Bergville AC Pipeline replacement by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD44 |  |  | 66 | Number of boreholes to be digitised at The Implementation of CITI-OS Water Infrastructure and Borehole Management System Phase 1 by 30/06/2026 | Number | Various | New Indicator | New Indicator | 17 boreholes to be digitised at The Implementation of CITI-OS Water Infrastructure and Borehole Management System Phase 1 by 31/12/2025 | 07 boreholes to be digitised at The Implementation of CITI-OS Water Infrastructure and Borehole Management System Phase 1 by 30/09/2025 | (0)boreholes to be digitised at The Implementation of CITI-OS Water Infrastructure and Borehole Management System Phase 1 by 30/09/2025 | 10 boreholes to be digitised at The Implementation of CITI-OS Water Infrastructure and Borehole Management System Phase 1 by 31/12/2025 | N/A | N/A | (0) boreholes digitised at The Implementation of CITI-OS Water Infrastructure and Borehole Management System Phase 1 by 31/12/2025 | Not Achieved | Delayed approval of the business plan | Contractor has been appointed on the 11 November 2025 to implement the project | Water, Sanitation & Technical Services | 15000000 |  | Signed Engineers Report
BSD45 |  |  | 67 | Number of 1.0ML concrete reservoir to be constructed at Langkloof Bulk water supply 1 by 30/06/2026 | Number | Various | New Indicator | New Indicator | 1 x 1.0MLconcrete reservoir to be constructed at Langkloof Bulk water supply 1 by 30/06/2026 | 1 x1.0MLconcrete reservoir to be constructed at Langkloof Bulk water supply 1 by 30/09/2025 | (1)1.0MLconcrete reservoir to be constructed at Langkloof Bulk water supply 1 by 30/09/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 18206891 | 893130.79 | Signed Engineers Report
BSD46 |  |  | 68 | Number communal standpipes to be installed at Langkloof Bulk water supply 1 by 30/06/2026 | Number | Various | New Indicator | New Indicator | 30 communal standpipes to be installed at Langkloof Bulk water supply 1 by 30/06/2026 | N/A | N/A | N/A | N/A | 30 communal standpipes to be installed at Langkloof Bulk water supply 1 by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD47 |  |  | 69 | Number of 1.5ML/d treatment package plant to be constructed at Langkloof Bulk water supply 1 by 30/06/2026 | Number | Various | New Indicator | New Indicator | 1 x 1.5ML/d treatment package plant to be constructed at Langkloof Bulk water supply 1 by 30/06/2026 | N/A | N/A | N/A | N/A | 1 x 1.5ML/d treatment package plant to be constructed at Langkloof Bulk water supply 1 by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD48 |  |  | 70 | Number of production boreholes to be drilled, equipped and tested at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 4 production boreholes to be drilled, equipped and tested at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | N/A | 4 production boreholes to be drilled, equipped and tested at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 20000000 |  | Signed Engineers Report
BSD49 |  |  | 71 | Number of pumps to be refurbished HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 2 pumps to be refurbished HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | N/A | 2 pumps to be refurbished HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD50 |  |  | 72 | Number of package plant treatment to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 4 package plant treatment to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | N/A | 4 package plant treatment be installed HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD51 |  |  | 73 | Number of water storage tanks to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 2 water storage tanks to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | 2 water storage tanks to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/03/2026 | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD52 |  |  | 74 | Number of Killometers of Rising main to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 2.95 Killometers of Rising main to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | 0.42 Killometers of Rising main to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/09/2025 | (0) Killometers of Rising main was not constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/09/2025 | 0.75 Killometers of Rising main to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/12/2025 | 0.77 Killometers of Rising main to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/03/2026 | 1.01 Killometers of Rising main to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | (0) Killometers of Rising main t constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/12/2025 | Not Achieved | Delays in introducing the project to the community. | Municipality to prioritize the community handovers | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD53 |  |  | 75 | Number of Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 2.116 Killometers of Bulk line to be comstructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | 0.30 Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/09/2025 | (0) Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/09/2025 | 0.54 Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/12/2025 | 0.55 Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/03/2026 | 0.72 Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | (0) Killometers of Bulk line to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/12/2025 | Not Achieved | Delays in introducing the project to the community. | Municipality to prioritize the community handovers | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD54 |  |  | 76 | Number of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | 2.206 of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | 0.32 of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/09/2025 | (0) of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/09/2025 | 0.56 of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/12/2025 | 0.58 of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/03/2026 | 0.75 of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | (0) of Killometers of Reticulation to be constructed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/12/2025 | Not Achieved | Delays in introducing the project to the community. | Municipality to prioritize the community handovers | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD55 |  |  | 77 | Number of standpipes to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | Number | Various | New Indicator | New Indicator | xxx of standpipes to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 30/06/2026 | N/A | N/A | N/A | xxx of standpipes to be installed at HOTSPOT AREAS - CES Turnkey Project for uThukela District Springs and Boreholes by 31/03/2026 | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  |  | Signed Engineers Report
BSD56 | To ensure safe and healthy potable water | Implement an effective water and waste water monitoring program | 78 | Number of water treatment plants monitored by 30/06/2026 | Number | Various | 15 water treatment plants monitored by 30/06/2024 | 15 water treatment plants monitored by 30/06/2024 | 15 water treatment plants monitored by 30/06/2026 | 15 water treatment plants monitored by 30/09/2025 | 15 | 15 water treatment plants monitored by 31/12/2025 | 15 water treatment plants monitored by 31/03/2026 | 15 water treatment plants monitored by 30/06/2026 | 42 | Not Achieved | Langkloof WTW found to be non-operational at the time of inspection. | Langkloof WTW under refurbishment | Water, Sanitation & Technical Services | OPEX |  | Signed Report
BSD57 |  |  | 79 | Number of waste water treatment works monitored by 30/06/2026 | Number | Various | 9 waste water treatment works monitored by 30/06/2024 | 9 waste water treatment works monitored by 30/06/2024 | 9 waste water treatment works monitored by 30/06/2026 | 9 waste water treatment works monitored by 30/09/2025 | 9 | 9 waste water treatment works monitored by 31/12/2025 | 9 waste water treatment works monitored by 31/03/2026 | 9 waste water treatment works monitored by 30/06/2026 | 24 | Not Achieved | Ekuvukeni WWTW innaccessable (locked)at the time of inspection. | Ekuvukeni WWTW to be refurbished. | Water, Sanitation & Technical Services | OPEX |  | Signed Report
BSD58 | To enhance consumer protection with sufficient food control | Monitor compliance of food sellling outlets | 80 | Number of food handling premises inspected by 30/06/2026 | Number | District -wide | 1118 food handling premises inspected by 30/06/2025 | 1118 food handling premises inspected by 30/06/2025 | 1080 food handling premises inspected by 30/06/2026 | 270 food handling premises inspected by 30/09/2025 | 371 food handling premises inspected by 30/09/2025 | 270 food handling premises inspected by 31/12/2025 | 270 food handling premises inspected by 31/03/2026 | 270 food handling premises inspected by 30/06/2026 | 274 food handling premises inspected by 31/12/2025 | Achieved | N/A | N/A | Community Services | OPEX |  | Signed reports
KPA3:LOCAL ECONOMIC DEVELOPMENT
LED01 | To Increase Job opportunities | Implement Expanded Public Works Programme (EPWP) | 81 | Number of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2026 | Number | District -wide | 1023 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2025 | 1023 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2025 | 1176 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2026 | N/A | N/A | N/A | N/A | 1176 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2026 | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | 1685000 | 44% | Signed reports
LED02 |  |  | 82 | Number of EPWP reports submitted to the funder by 30/06/2026 | Number | District -wide | 12 EPWP reports submitted to the funder by 30/06/2025 | 12 EPWP reports submitted to the funder by 30/06/2025 | 12 EPWP reports submitted to the funder by 30/06/2026 | 3 EPWP reports submitted to the funder by 30/09/2025 | 3 EPWP reports submitted to the funder by 30/09/2025 | 3 EPWP reports submitted to the funder by 31/12/2025 | 3 EPWP reports submitted to the funder by 31/03/2026 | 3 EPWP reports submitted to the funder by 30/06/2026 | 3 EPWP reports submitted to the funder by 31/12/2025 | Achieved |  |  | Water, Sanitation & Technical Services |  |  | Signed reports
LED03 | To Increase Job opportunities | Implement Expanded Public Works Programme (EPWP) | 83 | Number of FTE's created through LED initiatives, including capital projects, by 30/06/2026 | Number | District -wide | 372 FTE's jobs to be created through LED initiatives, including capital projects, by 30/06/2025 | 372 FTE's jobs to be created through LED initiatives, including capital projects, by 30/06/2025 | 423 FTE's jobs to be created through LED initiatives, including capital projects, by 30/06/2026 | N/A | N/A | N/A | N/A | 423 FTE's jobs to be created through LED initiatives, including capital projects, by 30/06/2026 | N/A | N/A | N/A |  | Water, Sanitation & Technical Service |  |  | Signed Reports
LED04 | To enhance the Uthukela Local Economic Development | LED policy reviewed | 84 | Date of review and adoption of LED strategy by Council 30/06/2026 | Date | n/a | Date of Review and adoption of LED strategy by Council by 30/06/2024 | LED strategy by Council by 28/05/2024 | Date of Review and adoption of LED strategy by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Date of Review and adoption of LED strategy by Council by 30/06/2026 | N/A | N/A | N/A |  | Community Services | OPEX | OPEX | Council Resolution and LED strategy
LED05 |  | Convene district LED/Tourism Forum meetings | 85 | Number of disrtict LED/Tourism forums meetings held by 30/06/2026 | Number | n/a | 4 disrtict LED/Tourism forums meetings held by 30/06/2025 | 4 disrtict LED/Tourism forums meetings held by 30/06/2025 | 4 disrtict LED/Tourism forums meetings held by 30/06/2026 | 1 disrtict LED/Tourism forums meeting held by 30/09/2025 | 1 disrtict LED/Tourism forums meeting was held on 23/09/2025 | 1 disrtict LED/Tourism forum meetings held by 31/12/2025 | 1 disrtict LED/Tourism forum meetings held by 31/03/2026 | 1 disrtict LED/Tourism forum meetings held by 30/06/2026 | 1 disrtict LED/Tourism forum meetings held by 31/12/2025 | Achieved | N/A | N/A | Community Services | OPEX | OPEX | Notice,Agenda, Attandance Register, Minutes
KP4: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM01 | To ensure legally sound financial viability and management | Timeous financial reporting and management | 86 | Percentange of MIG Expenditure by 30/06/2026 | Percentage | n/a | 100% of MIG expenditure by 30/06/2025 | 100% of MIG expenditure by 30/06/2025 | 100% of MIG expenditure by 30/06/2026 | 25% of MIG expenditure by 30/09/2025 | 18,19% of MIG expenditure by 30/09/2025 | 50% of MIG expenditure by 31/12/2025 | 75% of MIG expenditure by 31/03/2026 | 100% of MIG expenditure by 30/06/2026 | 71% of MIG expenditure by 31/12/2025 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | 211791439.81 | OPEX | Grant exenditure report and proof of payments
MFVM02 |  |  | 87 | Percentange of annual allocation to free basic services spent by 30/06/2026 | Percentage | n/a | 100% of annual allocation to free basic services spent by 30/06/2025 | 0% of annual allocation to free basic services spent by 30/06/2025 | 100% of annual allocation to free basic services spent by 30/06/2026 | 25% of annual allocation to free basic services spent by 30/09/2025 | 2,35% of annual allocation to free basic services spent by 30/09/2025 | 50% of annual allocation to free basic services spent by 31/12/2025 | 75% of annual allocation to free basic services spent by 31/03/2026 | 100% of annual allocation to free basic services spent by 30/06/2026 | 3,38% of annual allocation to free basic services spent by 31/12/2025 | Not Achieved | The municipality has system challenges which has requested assistance in resolving | The correct journals will be effected to resolve the under expenditure | Budget & Treasury Office | OPEX | OPEX | Signed reports
MFVM03 |  |  | 88 | Percentage of operating budget spent by 30/06/2025 | Percentage | n/a | 100% of operating budget spent by 30/06/2025 | 74% of operating budget spent by 30/06/2025 | 100% of operating budget spent by 30/06/2026 | 25% of operating budget spent by 30/09/2025 | 14,49% of operating budget spent by 30/09/2025 | 50% of operating budget spent by 31/12/2025 | 75% of operating budget spent by 31/03/2026 | 100% of operating budget spent by 30/06/2026 | 32% of operating budget spent by 31/12/2025 | Not Achieved | The municipality is implementing cost containment measures as its struggling with its cashflow | The municipality has to get a funded status | Budget & Treasury Office | 1192739920 | OPEX | Signed reports
MFVM04 |  |  | 89 | Percentange of capital budget spent by 30/06/2026 | Percentage | n/a | 100% of capital budget spent by 30/06/2025 | 100% of capital budget spent by 30/06/2025 | 100% of capital budget spent by 30/06/2026 | 25% of capital budget spent by 30/09/2025 | 1,75% of capital budget spent by 30/09/2025 | 50% of capital budget spent by 31/12/2025 | 75% of capital budget spent by 31/03/2026 | 100% of capital budget spent by 30/06/2026 | 16% of capital budget spent by 31/12/2025 | Not Achieved | Delays in capital projects | All projects will be awarded timely and spending will pick up in the next two quarters | Budget & Treasury Office | 289429000 | OPEX | Signed reports
MFVM05 |  |  | 90 | Percentange of repairs and maintenance spent by 30/06/2026 | Percentage | n/a | 100% of repairs and maintenance spent by 30/06/2025 | 38% of repairs and maintenance spent by 30/06/2011 | 100% of repairs and maintenance spent by 30/06/2026 | 25% of repairs and maintenance spent by 30/09/2025 | 0,16% of repairs and maintenance spent by 30/09/2025 | 50% of repairs and maintenance spent by 31/12/2025 | 75% of repairs and maintenance spent by 31/03/2026 | 100% of repairs and maintenance spent by 30/06/2026 | 25% of repairs and maintenance spent by 31/12/2025 | Not Achieved | The municipality is struggling with its cash position and applying cost containmnent | The municipality has to get a funded status | Budget & Treasury Office | 55000000 | OPEX | Signed reports
MFVM06 |  |  | 91 | Ratio on financial viability in terms of debt coverage by 30/06/2026 | Ratio | n/a | 1:03 | 8,49: 03 | 1:03 | 1:03 | 0.042361 | 1:03 | 1:03 | 1:03 | 01;1.59 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Signed reports
MFVM07 |  |  | 92 | Ratio on financial viability in terms of cost coverage by 30/06/2026 | Ratio | n/a | 1:02 | 1,47: 02 | 1:02 | 1:02 | 01:1,5 | 1:02 | 1:02 | 1:02 | 0.1:0.14 | Not Achieved | The municipality is struggling with its cash position and cannot pay all its expenditure by available cash | The municipality has to get a funded status | Budget & Treasury Office | OPEX | OPEX | Signed reports
MFVM08 |  |  | 93 | Ratio on financial viability in terms of outstanding service debtors to revenue by 30/06/2026 | Ratio | n/a | 1:01 | 0,14: 01 | 1:01 | 1:01 | 0.16.49 | 1:01 | 1:01 | 1:01 | 01;1.9 | Achived | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Signed reports
MFVM09 |  |  | 94 | Date of approval of 2026/2027 budget by 31/05/2026 | Date of approval | n/a | Approval of 2025/26 budget by 31/05/2022 | 2025/26 Budget was approved on the 28/05/2022 | Approval of 2026/27 budget by 31/05/2026 | N/A | N/A | N/A | N/A | Approval of 2025/25 budget by 31/05/2026 | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Council resolution
MFVM10 |  |  | 95 | Number of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2026 | Number |  | New Indicator | New Indicator | Twelve (12) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2026 | Twelve (12) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 September 2025 | Twelve (12) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 September 2025 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2025 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 March 2026 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2026 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2025 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Progress Reports, Proof of Submission to Treasury
MFVM11 |  |  | 96 | Date of submission of credible Annual Financial Statements to the Auditor-General by 31/08/2025 | Date | n/a | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2024 | Submitted credible Annual Financial Statements to the Auditor-Genral by 31/08/2024 | Date of Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2026 | Date of Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2025 | Credible Annual Financial Statements were submitted to the Auditor General on the 31/08/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Proof of submission and Annual Financial Statements
MFVM12 |  | Ensure legislative compliance | 97 | Number of Asset Register developed by 30/06/2026 | Number | n/a | 1 Asset Register developed by 30/06/2025 | 1 Asset Register developed by 30/06/2025 | 1Asset Register developed by 30/06/2026 | N/A | N/A | N/A | N/A | 1Asset Register developed by 30/06/2026 | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Asset Register
MFVM13 |  |  | 98 | Date of adoption of Finance related policies by Council by 31/05/2026 | Date | n/a | Adoption of Finance related policies by Council 31/05/2025 | Adoption of Finance related policies by Council 31/05/2025 | Date of Adoption of Finance related policies by Council 31/05/2026 | N/A | N/A | N/A | N/A | Date of Adoption of Finance related policies by Council 31/05/2026 | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | OPEX | Council Resolution
MFVM14 |  | Monitor the compliance with relevant legislation regarding financial expenditure | 99 | Percentage of reduction of Unauthorised, Irregular, Fruitless and Wasteful Expenditure by 30/06/2026 | Percentage | n/a | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2025 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2025 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2026 | 2% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/09/2025 |  | 5% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2025 | 8% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/03/2026 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2026 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2025 | Not Achieved | The municipality is struggling with reduction of UIF due to non payment of suppliers and the cashflow therof | The municipality has to get a funded status to avoid late payments and usage of same suppliers | All Departments | OPEX | OPEX | Signed Reports to Council
MFVM15 |  |  | 100 | Number of Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2026 | Number | n/a | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2025 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2025 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2026 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/09/2025 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/09/2025 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2025 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/03/2026 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/06/2026 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2025 | Achieved | N/A | N/A | All Departments | OPEX | OPEX | Signed Reports to Council
MFVM16 | To improve audit opinion | Implement an audit action plan | 101 | Percentage of audit queries raised by the Auditor-General addressed by 30/06/2026 | Percentage | n/a | 100% of audit queries raised by the Auditor-General addressed by 30/06/2025 | 95% of of audit queries raised by the Auditor-General addressed by 30/06/2025 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2026 | 25% of audit queries raised by the Auditor-General addressed by 30/09/2025 |  | 50% of audit queries raised by the Auditor-General addressed by 31/12/2025 | 75% of audit queries raised by the Auditor-General addressed by 31/03/2026 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2026 |  |  |  |  | All Departments | OPEX | OPEX | Audit action plan and dashboard report
KPA5:Good Governance and Puplic Participation
GGPP01 | To ensure good and effective governance | Ensure Participation in the IGR Structures | 102 | Percentage of functional IGR Structures coordinated by 30/06/2026 | Percentage | n/a | 100% of functional IGR Structures by 30/06/2025 | 100% of functional IGR Structures by 30/06/2025 | 100% of functional IGR Structures coordinated by 30/06/2026 | 100% of functional IGR Structures coordinated by 30/09/2025 | 50% of functional IGR Structures coordinated by 30/09/2025 | 100% of functional IGR Structures coordinated by 31/12/2025 | 100% of functional IGR Structures coordinated by 31/03/2026 | 100% of functional IGR Structures coordinated by 30/06/2026 |  |  |  |  | Office of the MM | OPEX | OPEX | Notice, minutes & attendance registers
GGPP02 | To promote the interest of designated groups | Enhance Stakeholder Relation and Public Participation | 103 | Number of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 30/06/2025 | Number | n/a | New Indicator | New Indicator | Four (4) of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 30/06/2026 | One (1) of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 30/09/2025 | One (1) of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 30/09/2025 | One (1) of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 31/12/2025 | One (1) of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 31/03/2026 | One (1) of Reports on Mayoral Activities ( Special Programmes,Youth,Public Participation,Operation Sukuma Sakhe) submitted to Council by 30/06/2026 |  |  |  |  | Office of the MM | OPEX | OPEX | Signed Report,Council Resolution
KPA6:Cross Cutting Issues
CCI01 | Efficient & Credible Stratgic & Spatial Municipal Planning | Revision of a Credible Intergrated Development Plan | 104 | Date of review and adoption of credible integrated development planning by Council by 31/05/2026 | Date | n/a | Review and adoption of credible integrated development planning by Council by 31/05/2025 | Reviewed and adopted credible integrated development planning on the 28/05/2025 | Date of Review and adoption of credible integrated development planning by Council by 31/05/2026 | N/A | N/A | N/A | N/A | Date of Review and adoption of credible integrated development planning by Council by 31/05/2026 | N/A | N/A | N/A | N/A | Office of the MM | OPEX | OPEX | Council resolution and Integrated development plan
CCI02 | To ensure the implementation of Spatial Development Framework | Improved Spatial Development Framework | 105 | Date of review and adoption of district Spatial Development framework by Council by 31/05/2026 | Date | n/a | Review and adoption of district Spatial Development framework by Council by 31/05/2025 | Reviewed and adopted district Spatial Development framework by Council on the 31/05/2025 | Review and adoption of district Spatial Development framework by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Date of Review and adoption of district Spatial Development framework by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Community Services | OPEX | OPEX | Council resolution and Spatial Development framework
CCI03 | To ensure sustainable protection and development of the environment | Development and implementation of environmental management Plan | 106 | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2026 | Date | All | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2025 | Reviewed and Adopted Environmental Management Plan by Council by 28/05/2025 | Review and adoption of Environmental Management Plan provided by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Date of Review Review and adoption of Environmental Management Plan provided by Council by 30/06/2026 | N/A | N/A | N/A | N/A | Community Services | OPEX | OPEX | Council Resolution and Environmental Management Plan
CCI04 | To create a safety and responsive environment to the community | Attending and responding to disasters and incidents with a district | 107 | Date of Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2026 | Date | n/a | New Indicator | New Indicator | Date of Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2026 | N/A | N/A | N/A | N/A | Date of Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2026 | N/A | N/A | N/A | N/A | Community Services | OPEX | OPEX | Disaster Management Annual Report,Council Resolution
CCI05 |  |  | 108 | Number Of Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2026 | Number | District -wide | New Indicator | New Indicator | Four (4)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2026 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/09/2025 | One (1)Awareness Campaigns on Disaster was provided to the UTDM Community by 30/09/2025 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2025 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/03/2026 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2026 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2025 | Achieved |  |  | Community Services | OPEX | OPEX | Dated Report
CCI06 | To ensure proper communication with the public | Monitor the functioning and eficient of the Municipal Call Centre | 109 | Date of Review of the Call Centre Charter submitted to Council by 30/06/2026 | Date | n/a | New Indicator | New Indicator | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2026 | N/A | N/A | N/A | N/A | Date of Review of the UTDM Call Centre Charter submitted to Council by 30/06/2026 | N/A | N/A | N/A | N/A | Community Services | OPEX | OPEX | Call Centre Charter,Council Resolution